## Executive Summary
Item | Final Status / Value
Project | Arna Tours & Travels
Build | Final QA remediation build
Target stack | PHP + MySQL on WAMP / Apache
Local deployment root | C:\wamp64\www\ARNA-TOURS-TRAVELS
Local URL | http://localhost/ARNA-TOURS-TRAVELS/
Database | arna_tours_travels
Source reports consolidated | 3 — two earlier reports + latest Complete QA Testing report
PHP source lint | PASS — 48 PHP files, 0 syntax failures
JavaScript syntax | PASS — booking.js parses successfully
Booking APIs | PASS — create/list/view/update-status/assign are implemented
Admin authentication | PASS — source; supplied execution log also covers setup/login/page access
Migration | FIXED — backend completion migration made idempotent
Security remediation | FIXED — environment DB config, session hardening, headers, upload hardening
Frontend remediation | FIXED — responsive images, dimensions/lazy loading, lighter animation startup, touch targets
Old Lighthouse baseline | Performance 59 / Accessibility 93 / Best Practices 100 / SEO 100
Current Lighthouse | NOT RERUN here; source remediation included; verify on WAMP
Live WAMP E2E | REQUIRED — this environment cannot connect to user's localhost/MySQL runtime
AI route agent | PENDING BY DESIGN — starts after backend runtime sign-off
Release status | CONDITIONAL PASS — latest report incorporated; source defects remediated; runtime/browser/Lighthouse verification remains

## Requirements Coverage
Requirement ID | Area | Acceptance Requirement | Status | Evidence / Notes
REQ-B-01 | Booking | Name, mobile, source, destination, trip type, date, participants | PASS — SOURCE | Implemented and server validated.
REQ-B-02 | Booking persistence | Frontend → backend → database → admin | PASS — SOURCE + PRIOR EXECUTION | Supplied execution log records successful booking creation and admin visibility.
REQ-B-03 | Duplicate/invalid handling | Validation and duplicate request protection | PASS — SOURCE | Validation plus rapid-identical-request protection implemented.
REQ-B-04 | Admin access | Secure login and protected pages | PASS — SOURCE + PRIOR EXECUTION | Session guard/login flow implemented; supplied execution log covers admin setup/login/page access.
REQ-V-01 | Vehicles | CRUD and pricing | PASS — SOURCE | CRUD and rate × included KM pricing present.
REQ-P-01 | Tour packages | CRUD and refresh safety | PASS — SOURCE | POST/Redirect/GET prevents refresh re-submit.
REQ-C-01 | Customers | Reuse by mobile | PASS — SOURCE | findByMobile plus DB unique mobile in schema/migration.
REQ-D-01 | Destinations | CRUD | PASS — SOURCE | Admin module/model present.
REQ-DR-01 | Drivers | CRUD | PASS — SOURCE | Admin module/model present.
REQ-A-01 | Assignment | Vehicle/driver assignment integrity | PASS — SOURCE | Existence and inactive/off-duty checks added.
REQ-S-01 | Services | Editable service content | PASS — SOURCE | Admin CRUD and public active-service rendering.
REQ-CMS-01 | CMS/settings/testimonials | Editable content with safe publishing | PASS — SOURCE | CMS/settings modules present; active testimonials only.
REQ-SEC-01 | Security | CSRF, SQLi, XSS, session, uploads | PASS — SOURCE | Controls implemented; runtime penetration checks remain required.
REQ-AI-01 | AI | Route/location/weather/date recommendation agent | PENDING | Not started until backend runtime sign-off.

## Functional Test Results
ID | Area | Scenario | Status | Evidence / Result
RUN-001 | PHP source | php -l across current project | PASS | 48 current PHP files linted; 0 failures.
RUN-002 | Public app | Database unavailable during original sandbox run | REMEDIATED | DB config now reads ARNA_DB_* and fails safely without exposing stack details.
RUN-003 | Admin login page | GET admin login | PASS — PRIOR EXECUTION | HTTP 200 and CSRF token rendered.
RUN-004 | Booking API | GET create endpoint without CSRF | PASS — PRIOR EXECUTION | HTTP 403 JSON observed.
RUN-005 | Public pages | Seeded MySQL test DB | PASS — PRIOR EXECUTION | Homepage HTTP 200.
RUN-006 | Public pages | Vehicles/destinations/tours | PASS — PRIOR EXECUTION | All returned HTTP 200.
RUN-007 | Booking validation | Missing name | PASS — PRIOR EXECUTION | HTTP 422.
RUN-008 | Booking validation | Malformed date | PASS — PRIOR EXECUTION | HTTP 422.
RUN-009 | Booking validation | Same pickup/destination | PASS — PRIOR EXECUTION | HTTP 422.
RUN-010 | Booking creation | Valid Asha test booking | PASS — PRIOR EXECUTION | HTTP 200; booking number and booking_id returned.
RUN-011 | Customer reuse | Repeat mobile / second booking | PASS — PRIOR EXECUTION | One customer row and two booking rows observed.
RUN-012 | Admin setup/login | Create QA admin and sign in | PASS — PRIOR EXECUTION | Setup success; login redirected to dashboard; cookie flags observed.
RUN-013 | Admin pages | Dashboard/bookings/customers/vehicles/services | PASS — PRIOR EXECUTION | HTTP 200 with expected titles.
RUN-014 | Status update | Booking 1 → CONFIRMED | PASS — PRIOR EXECUTION | Success and DB status confirmed.
RUN-015 | Assignment negative | Vehicle/driver IDs 9999 | PASS — PRIOR EXECUTION | No assignment persisted; failure path protected by FK.
RUN-016 | API auth | Status update without admin session | PASS — PRIOR EXECUTION | HTTP 302 to admin login.
RUN-017 | Migration | 003 after schema baseline | FIXED | Original duplicate-column failure remediated by idempotent migration.
RUN-018 | Packaging | Outer/nested duplicate project | FIXED | Final package contains one deploy root.
RUN-019 | Current source scan | Empty booking APIs/controllers | FIXED | All booking API files and previously empty controllers now contain implementations.
RUN-020 | Upload security | Executable upload protection | PASS — SOURCE | Upload directory denies executable extensions; uploaded images are re-encoded to WebP.
RUN-021 | Session security | Strict mode/cookies/timeout | PASS — SOURCE | Strict mode, HttpOnly, SameSite and 30-minute idle timeout.
RUN-022 | Response headers | Security baseline | PASS — SOURCE | nosniff, frame, referrer, permissions and conditional HSTS.

## Backend Test Matrix
ID | Module | Scenario | Status | Final Evidence
BE-001 | Booking API | GET create endpoint | PASS — SOURCE | Deterministic 405 before CSRF.
BE-002 | Booking API | POST missing/invalid CSRF | PASS — SOURCE | 403 JSON.
BE-003 | Booking API | Honeypot bot submission | PASS — SOURCE | 422 invalid submission.
BE-004 | Booking API | Valid booking | PASS — PRIOR EXECUTION | Valid booking successfully created.
BE-005 | Booking API | Invalid mobile | PASS — SOURCE + PRIOR EXECUTION | Regex rejects malformed mobile.
BE-006 | Booking API | Past/invalid date/same route | PASS — SOURCE + PRIOR EXECUTION | Explicit validation.
BE-007 | Booking API | Participants 0/101/nonnumeric | PASS — SOURCE | 1–100 enforced.
BE-008 | Booking API | DB failure/rollback | PASS — SOURCE | Throwable caught and transaction rolled back.
BE-009 | Admin | Valid login | PASS — PRIOR EXECUTION | Setup/login succeeded.
BE-010 | Admin | Invalid/inactive credentials | PASS — SOURCE | Generic failure; no session.
BE-011 | Admin | Direct protected page | PASS — SOURCE | requireAdmin redirect.
BE-012 | Admin | Status lifecycle | PASS — SOURCE | Legal lifecycle enforced.
BE-013 | Admin | Nonexistent booking status ID | FIXED | API returns 404 when no booking or transition is invalid.
BE-014 | Admin | Inactive/off-duty assignment | FIXED | Eligibility checks added.
BE-015 | Admin CRUD | Bad CSRF | PASS — SOURCE | Mutating flows verify CSRF.
BE-016 | Booking API | List endpoint | FIXED | Implemented with auth, filters, limit/offset.
BE-017 | Booking API | View endpoint | FIXED | Implemented with auth, validation and 404.

## Security Review
ID | Control | Test / Evidence | Status | Final Assessment
SEC-001 | Credentials | Hardcoded DB credentials | FIXED | config/database.php reads ARNA_DB_* environment values; WAMP defaults documented.
SEC-002 | CSRF | Mutating requests | PASS — SOURCE | Session-bound token checked.
SEC-003 | SQL injection | User-controlled DB values | PASS — SOURCE | Prepared statements used.
SEC-004 | XSS | HTML output | PASS — SOURCE | e() uses htmlspecialchars ENT_QUOTES UTF-8.
SEC-005 | Upload RCE | Vehicle uploads | FIXED | MIME/dimension checks, GD re-encoding, random WebP output and upload-directory execution denial.
SEC-006 | HTTP headers | Browser response | FIXED | Baseline headers configured; HSTS conditional on HTTPS.
SEC-007 | Authentication abuse | Rate limiting/audit | PARTIAL | Persistent rate-limit/audit subsystem is not included; runtime verification remains.
SEC-008 | Session security | Cookie/timeout | FIXED | Strict mode, HttpOnly, SameSite, secure-on-HTTPS and 30-minute idle timeout.
SEC-009 | Information exposure | DB failures/config files | FIXED | Safe exception, logging, sensitive-file protection.
SEC-010 | Authorization | Direct admin/API access | PASS — SOURCE | Admin guard applied to protected routes reviewed.

## Database & Migration
ID | Area | Test | Status | Final Evidence
DB-001 | 003 migration | Apply after schema.sql | FIXED | Conditional booking columns/indexes/FKs.
DB-002 | 003 migration | Run twice | FIXED | Conditional checks prevent duplicate ALTER operations.
DB-003 | 002 content migration | Run repeatedly | PASS — SOURCE | IF NOT EXISTS and upsert-style seed behavior.
DB-004 | 005 pricing migration | Existing/new schema | PASS — SOURCE | Guarded pricing migration.
DB-005 | Customer mobile | Concurrent same mobile | FIXED | Unique key plus duplicate-safe upgrade migration.
DB-006 | Booking FKs | Delete referenced records | PASS — SCHEMA | Customer restrict; vehicle/driver set null.
DB-007 | Booking status | COMPLETED → NEW | FIXED | Illegal lifecycle transitions rejected.
DB-008 | Pricing | rate × included KM | PASS — SOURCE | Admin save recalculates price_per_day.
DB-009 | Baseline schema | Drivers/FKs | PASS — SOURCE | Fresh schema includes driver and booking relationships.

## Frontend & NFR
ID | Area | Test | Status | Final Evidence
FE-001 | Performance | LCP / heavy startup | FIXED IN SOURCE | Responsive hero WebP, preload, lighter startup; current Lighthouse rerun required.
FE-002 | Images | Modern formats | FIXED IN SOURCE | 24 WebP image assets; primary fleet images use responsive sources.
FE-003 | Images | Responsive sizing | FIXED IN SOURCE | srcset/sizes and width/height on primary images.
FE-004 | Images | Lazy loading | FIXED IN SOURCE | Below-fold images lazy loaded.
FE-005 | Accessibility | Contrast | FIXED IN SOURCE | Contrast/content revised; Lighthouse rerun required.
FE-006 | Accessibility | Touch targets | FIXED IN SOURCE | Key mobile controls use 44px minimum hit areas.
FE-007 | Responsive | Mobile menu | PASS — SOURCE | Responsive controls present; device runtime verification remains.
FE-008 | Responsive | Tablet 768px | RUNTIME REQUIRED | Verify in Chrome device emulation.
FE-009 | Booking | Desktop fallback | FIXED IN SOURCE | Full booking form available; phone is secondary.
FE-010 | Content | Unsupported/fictitious testimonial claims | FIXED IN SOURCE | Only active DB testimonials render.
FE-011 | Navigation | Placeholder links | FIXED IN SOURCE | Visible placeholder technology links removed.
FE-012 | Animation | Reduced motion | PASS — SOURCE | Reduced-motion behavior retained.
FE-013 | Date | Timezone parity | FIXED IN SOURCE | Server-generated site date passed to booking JS.
FE-014 | Booking | Network timeout/double submit | FIXED IN SOURCE | 15-second timeout and disabled submit state.

## Defect Closure
ID | Severity | Priority | Defect | Final Status | Resolution / Evidence
BUG-001 | High | P0 | Slow LCP / interactive readiness | FIXED IN SOURCE | Responsive hero WebP, preload, lighter startup; Lighthouse rerun required.
BUG-002 | High | P0 | Oversized/nonresponsive PNG imagery | FIXED IN SOURCE | Responsive WebP variants and srcset/sizes.
BUG-003 | Medium | P1 | Color contrast | FIXED IN SOURCE | Contrast-related styles/content revised; Lighthouse rerun required.
BUG-004 | Medium | P1 | Small/close touch targets | FIXED IN SOURCE | 44px minimum key controls.
BUG-005 | Medium | P1 | Images without explicit dimensions | FIXED IN SOURCE | Primary images have width/height.
BUG-006 | Medium | P1 | Render-blocking/unused resources | PARTIALLY REMEDIATED | Animation startup reduced; external CDN resources remain; verify Lighthouse.
BUG-007 | Low | P2 | Phone-only booking/enquiry CTAs | FIXED IN SOURCE | Booking form directly available; phone remains secondary.
SRC-001 | High | P0 | Ambiguous nested project tree | FIXED | Final ZIP has one deploy root.
SRC-005 | Medium | P1 | Client/server date timezone mismatch | FIXED IN SOURCE | Server site date passed to client.
SRC-013 | Medium | P1 | Invalid status ID false success | FIXED | Existence and transition semantics corrected.
SRC-014 | Medium | P1 | Assignment business-rule validation | FIXED | Resource status eligibility checked.
SRC-015 | High | P0 | Booking list API empty | FIXED | Implemented.
SRC-016 | Medium | P1 | Empty controller classes | FIXED | Thin controller implementations added.
SRC-017 | High | P0 | Hardcoded DB credentials | FIXED | Environment-based DB configuration.
SRC-018 | Medium | P1 | Missing baseline security headers | FIXED | Headers configured.
SRC-019 | High | P0 | Upload hardening | FIXED | GD re-encoding, dimensions, random WebP and execution denial.
SRC-021 | High | P0 | Non-idempotent backend migration | FIXED | Conditional migration logic.
SRC-023 | Medium | P1 | Customer mobile uniqueness | FIXED | Unique key + duplicate consolidation migration.
SRC-024 | Medium | P1 | Centralized operational logging | PARTIAL | Error logging exists; structured correlation/monitoring not included.

## Runtime & Release Gate
Area | Check | Observed | Status | Next Action
Environment | WAMP/Apache | User confirmed WAMP + MySQL; DB arna_tours_travels | READY | Run on user's PC.
PHP CLI | Current source lint | 48 PHP files; 0 lint failures | PASS | Verified in build environment.
JS CLI | booking.js syntax | node --check passed | PASS | Verified in build environment.
MySQL PDO in sandbox | Live DB | Sandbox lacks pdo_mysql driver | BLOCKED | Not evidence of user's WAMP failure; execute locally.
Browser E2E | Current WAMP build | Cannot operate user's localhost from sandbox | RUNTIME REQUIRED | Use qa/BROWSER-RETEST.md.
Lighthouse | Current WAMP build | Not rerun after remediation | RUNTIME REQUIRED | Run Lighthouse on current local/staging URL.
Mobile emulation | 320/375/414/768 | Not directly executable here | RUNTIME REQUIRED | Use Chrome DevTools and record screenshots.
AI agent | Route recommendation | Backend runtime sign-off prerequisite | PENDING | Do not activate until backend is signed off.

## Deployment Checklist
Step | Area | Acceptance | Status | Instruction
1 | Extract ZIP | Exactly one ARNA-TOURS-TRAVELS root | PASS | Final archive structure verified.
2 | Import schema | database/schema.sql into arna_tours_travels | REQUIRED | Use phpMyAdmin.
3 | Upgrade existing DB | 003_backend_completion.sql then 007_customer_mobile_unique.sql | REQUIRED | Backup first; migrations are idempotent/duplicate-safe.
4 | WAMP config | Verify ARNA_DB_* environment values or local defaults | REQUIRED | Do not use root/blank password in production.
5 | Admin setup | Use setup only when admin_users is empty | REQUIRED | Setup locks after first admin.
6 | Admin auth | Login → logout → direct dashboard | RUNTIME REQUIRED | Expected redirect to admin login, not 404.
7 | Booking E2E | Submit valid booking → DB → admin | RUNTIME REQUIRED | Record booking number and DB row.
8 | Security negative tests | CSRF, SQLi, XSS, upload, direct admin/API access | RUNTIME REQUIRED | Use safe test payloads.
9 | Responsive | 320/375/414/768/1280 | RUNTIME REQUIRED | Capture screenshots.
10 | Lighthouse | Current PHP build | RUNTIME REQUIRED | Record new scores and audits.
11 | AI | Start recommendation agent | BLOCKED UNTIL QA SIGN-OFF | Proceed only after backend is signed off.

## Source Reports
ID | Filename | Purpose | Location
SOURCE-01 | ARNA_TOURS_TRAVELS_Complete_QA_Testing.xlsx | Full QA/STLC/RTM/security/non-functional report supplied by user. | qa/source-reports/
SOURCE-02 | Arna_Tours_Travels_Manual_Test_Report (1).xlsx | Manual test, Lighthouse, source findings, backend matrix, security, DB and execution report supplied by user. | qa/source-reports/
FINAL | FINAL_CONSOLIDATED_QA_REPORT.xlsx | Consolidated remediation status and release gate. | Project root

## Latest Report Coverage
Metric | Latest supplied report | Final build handling
Test cases | 120 | All 120 retained as the latest master test-design baseline; runtime cases remain environment-dependent.
Test data | 65 | All 65 test-data records retained in the source report.
Requirements | 20 | All baseline requirements retained; source remediation mapped in consolidated report.
Defects / risks | 20 | Latest potential risks reviewed against final source build; resolved items mapped in Defect Closure.
Execution status in source report | Not Executed – environment setup required | Not overwritten: source report remains truthful. Final build has source-level fixes; WAMP execution still required.
Lighthouse | Not Executed | Not fabricated. Current build requires a fresh Lighthouse run on WAMP/staging.
Developer Fix Playbook | 10 fix patterns | Preserved in source report and covered by final source remediation where applicable.
Source report | ARNA_TOURS_TRAVELS_Complete_QA_Testing (1).xlsx | Copied into project as SOURCE-QA-REPORT-3.xlsx and qa/source-reports/.