## Read Me
ARNA TOURS & TRAVELS — Complete QA Workbook
Prepared from ARNA-TOURS-TRAVELS.zip ¦ Static baseline date: 2026-09-17 ¦ Status discipline: unexecuted is not pass
Section | Details
Purpose | Complete QA workbook for ARNA-TOURS-TRAVELS supplied ZIP. It combines static inspection, executable manual test design, test data, expected results, RTM, defect lifecycle and release guidance.
Scope | Public PHP pages: index.php, vehicles.php, tours.php, destinations.php; booking UI/API; admin modules; database/schema and SQL migrations; JS/CSS/assets.
Execution status | The archive was extracted and statically inspected. Browser/API/DB execution is marked “Not Executed – environment setup required” unless separately evidenced. Do not treat unexecuted cases as pass.
Environment needed | PHP web server, MySQL/MariaDB loaded with database/*.sql, configured DB credentials, a seeded admin account, browser matrix, Lighthouse/DevTools, and test email/phone data.
Release gates | All Critical functional/security cases pass; no open Critical/High defects without approved risk; smoke/sanity pass; Lighthouse/accessibility results recorded; backup/cleanup completed.
How to use | Filter Test Cases by Test Type/Priority/Status. Execute with Test Data IDs. Record Actual Result, Evidence, Defect ID and final status in Execution Log. Use RTM for coverage and Defects for lifecycle/fix guidance.
Important assumption | Future dates use 2099-01-01 so they remain future-dated; TD-001 uses today and must be adjusted to a future date if execution occurs after today.
Static quality checks | PHP lint output is saved alongside the workbook in the working directory; inspect it before release. Lighthouse requires a running HTTP origin and was not run against the ZIP directly.
Workbook tabs
File Inventory
Requirements
Test Data
Test Cases
Execution Log
RTM Matrix
Defect Log
Defect Lifecycle
STLC SDLC Plan
QA QC Glossary
Non-Functional Plan
Lighthouse Log
Executive Summary

## File Inventory
Extracted File Inventory
All files extracted under /home/ubuntu/work/arna/ARNA-TOURS-TRAVELS; source ZIP retained separately.
Relative Path | Extension | Size (bytes) | Category | Inspection Status
.htaccess | [no extension] | 556 | Asset/document | Inventory only
ARNA-TOURS-TRAVELS/.htaccess | [no extension] | 556 | Asset/document | Inventory only
ARNA-TOURS-TRAVELS/QA-UPDATE.md | .md | 1321 | Asset/document | Inspected
ARNA-TOURS-TRAVELS/RUN-ME.txt | .txt | 0 | Asset/document | Inspected
ARNA-TOURS-TRAVELS/SETUP-V2.md | .md | 1471 | Asset/document | Inspected
ARNA-TOURS-TRAVELS/admin/admin-layout.php | .php | 3263 | Application/source | Inspected
ARNA-TOURS-TRAVELS/admin/booking-view.php | .php | 5272 | Application/source | Inspected
ARNA-TOURS-TRAVELS/admin/bookings.php | .php | 2510 | Application/source | Inspected
ARNA-TOURS-TRAVELS/admin/cms.php | .php | 5630 | Application/source | Inspected
ARNA-TOURS-TRAVELS/admin/customers.php | .php | 1866 | Application/source | Inspected
ARNA-TOURS-TRAVELS/admin/dashboard.php | .php | 2387 | Application/source | Inspected
ARNA-TOURS-TRAVELS/admin/destinations.php | .php | 5997 | Application/source | Inspected
ARNA-TOURS-TRAVELS/admin/drivers.php | .php | 6084 | Application/source | Inspected
ARNA-TOURS-TRAVELS/admin/index.php | .php | 3249 | Application/source | Inspected
ARNA-TOURS-TRAVELS/admin/logout.php | .php | 349 | Application/source | Inspected
ARNA-TOURS-TRAVELS/admin/packages.php | .php | 7585 | Application/source | Inspected
ARNA-TOURS-TRAVELS/admin/services.php | .php | 5428 | Application/source | Inspected
ARNA-TOURS-TRAVELS/admin/settings.php | .php | 2343 | Application/source | Inspected
ARNA-TOURS-TRAVELS/admin/setup.php | .php | 2820 | Application/source | Inspected
ARNA-TOURS-TRAVELS/admin/vehicles.php | .php | 12199 | Application/source | Inspected
ARNA-TOURS-TRAVELS/api/booking/assign.php | .php | 875 | Application/source | Inspected
ARNA-TOURS-TRAVELS/api/booking/create.php | .php | 4817 | Application/source | Inspected
ARNA-TOURS-TRAVELS/api/booking/list.php | .php | 0 | Application/source | Inspected
ARNA-TOURS-TRAVELS/api/booking/update-status.php | .php | 832 | Application/source | Inspected
ARNA-TOURS-TRAVELS/api/booking/view.php | .php | 0 | Application/source | Inspected
ARNA-TOURS-TRAVELS/assets/css/admin.css | .css | 7754 | Application/source | Inventory only
ARNA-TOURS-TRAVELS/assets/css/booking.css | .css | 8066 | Application/source | Inventory only
ARNA-TOURS-TRAVELS/assets/css/responsive-fix.css | .css | 5499 | Application/source | Inventory only
ARNA-TOURS-TRAVELS/assets/css/scroll-car.css | .css | 2862 | Application/source | Inventory only
ARNA-TOURS-TRAVELS/assets/css/styles.css | .css | 11609 | Application/source | Inventory only
ARNA-TOURS-TRAVELS/assets/css/swiper-bundle.min.css | .css | 18431 | Application/source | Inventory only
ARNA-TOURS-TRAVELS/assets/img/car-1.png | .png | 423629 | Asset/document | Inventory only
ARNA-TOURS-TRAVELS/assets/img/car-2.png | .png | 452458 | Asset/document | Inventory only
ARNA-TOURS-TRAVELS/assets/img/car-3.png | .png | 420556 | Asset/document | Inventory only
ARNA-TOURS-TRAVELS/assets/img/ertiga.png | .png | 1688131 | Asset/document | Inventory only
ARNA-TOURS-TRAVELS/assets/img/etios.png | .png | 1641587 | Asset/document | Inventory only
ARNA-TOURS-TRAVELS/assets/img/favicon.png | .png | 1067 | Asset/document | Inventory only
ARNA-TOURS-TRAVELS/assets/img/innova.png | .png | 1874009 | Asset/document | Inventory only
ARNA-TOURS-TRAVELS/assets/js/booking.js | .js | 6444 | Application/source | Inspected
ARNA-TOURS-TRAVELS/assets/js/gsap.min.js | .js | 72214 | Application/source | Inspected
ARNA-TOURS-TRAVELS/assets/js/main.js | .js | 2142 | Application/source | Inspected
ARNA-TOURS-TRAVELS/assets/js/scroll-car.js | .js | 6229 | Application/source | Inspected
ARNA-TOURS-TRAVELS/assets/js/swiper-bundle.min.js | .js | 150447 | Application/source | Inspected
ARNA-TOURS-TRAVELS/assets/uploads/.htaccess | [no extension] | 97 | Asset/document | Inventory only
ARNA-TOURS-TRAVELS/assets/uploads/vehicles/vehicle-47285ae299848e807264.png | .png | 420556 | Asset/document | Inventory only
ARNA-TOURS-TRAVELS/booking.php | .php | 88 | Application/source | Inspected
ARNA-TOURS-TRAVELS/config/api_keys.php | .php | 0 | Application/source | Inspected
ARNA-TOURS-TRAVELS/config/config.php | .php | 259 | Application/source | Inspected
ARNA-TOURS-TRAVELS/config/database.php | .php | 1111 | Application/source | Inspected
ARNA-TOURS-TRAVELS/contact.php | .php | 0 | Application/source | Inspected
ARNA-TOURS-TRAVELS/controllers/BookingController.php | .php | 2398 | Application/source | Inspected
ARNA-TOURS-TRAVELS/controllers/CustomerController.php | .php | 0 | Application/source | Inspected
ARNA-TOURS-TRAVELS/controllers/RecommendationController.php | .php | 0 | Application/source | Inspected
ARNA-TOURS-TRAVELS/controllers/TourController.php | .php | 0 | Application/source | Inspected
ARNA-TOURS-TRAVELS/controllers/VehicleController.php | .php | 0 | Application/source | Inspected
ARNA-TOURS-TRAVELS/database/002_content_management.sql | .sql | 3695 | Application/source | Inspected
ARNA-TOURS-TRAVELS/database/003_backend_completion.sql | .sql | 2969 | Application/source | Inspected
ARNA-TOURS-TRAVELS/database/005_vehicle_pricing.sql | .sql | 4018 | Application/source | Inspected
ARNA-TOURS-TRAVELS/database/schema.sql | .sql | 8281 | Application/source | Inspected
ARNA-TOURS-TRAVELS/destinations.php | .php | 1405 | Application/source | Inspected
ARNA-TOURS-TRAVELS/includes/auth.php | .php | 1153 | Application/source | Inspected
ARNA-TOURS-TRAVELS/includes/footer.php | .php | 0 | Application/source | Inspected
ARNA-TOURS-TRAVELS/includes/functions.php | .php | 2345 | Application/source | Inspected
ARNA-TOURS-TRAVELS/includes/header.php | .php | 0 | Application/source | Inspected
ARNA-TOURS-TRAVELS/index.php | .php | 71587 | Application/source | Inspected
ARNA-TOURS-TRAVELS/models/Booking.php | .php | 4803 | Application/source | Inspected
ARNA-TOURS-TRAVELS/models/Cms.php | .php | 1150 | Application/source | Inspected
ARNA-TOURS-TRAVELS/models/Customer.php | .php | 1627 | Application/source | Inspected
ARNA-TOURS-TRAVELS/models/Destination.php | .php | 1777 | Application/source | Inspected
ARNA-TOURS-TRAVELS/models/Driver.php | .php | 1743 | Application/source | Inspected
ARNA-TOURS-TRAVELS/models/Service.php | .php | 2042 | Application/source | Inspected
ARNA-TOURS-TRAVELS/models/TourPackage.php | .php | 1703 | Application/source | Inspected
ARNA-TOURS-TRAVELS/models/Vehicle.php | .php | 3983 | Application/source | Inspected
ARNA-TOURS-TRAVELS/tours.php | .php | 1411 | Application/source | Inspected
ARNA-TOURS-TRAVELS/vehicles.php | .php | 5104 | Application/source | Inspected
QA-UPDATE.md | .md | 1321 | Asset/document | Inspected
RUN-ME.txt | .txt | 0 | Asset/document | Inspected
SETUP-V2.md | .md | 1471 | Asset/document | Inspected
admin/admin-layout.php | .php | 3263 | Application/source | Inspected
admin/booking-view.php | .php | 5013 | Application/source | Inspected
admin/bookings.php | .php | 2510 | Application/source | Inspected
admin/cms.php | .php | 5447 | Application/source | Inspected
admin/customers.php | .php | 1866 | Application/source | Inspected
admin/dashboard.php | .php | 2387 | Application/source | Inspected
admin/destinations.php | .php | 5819 | Application/source | Inspected
admin/drivers.php | .php | 5916 | Application/source | Inspected
admin/index.php | .php | 3249 | Application/source | Inspected
admin/logout.php | .php | 349 | Application/source | Inspected
admin/packages.php | .php | 14302 | Application/source | Inspected
admin/services.php | .php | 5236 | Application/source | Inspected
admin/settings.php | .php | 2237 | Application/source | Inspected
admin/setup.php | .php | 2820 | Application/source | Inspected
admin/vehicles.php | .php | 15927 | Application/source | Inspected
api/booking/assign.php | .php | 875 | Application/source | Inspected
api/booking/create.php | .php | 4817 | Application/source | Inspected
api/booking/list.php | .php | 0 | Application/source | Inspected
api/booking/update-status.php | .php | 832 | Application/source | Inspected
api/booking/view.php | .php | 0 | Application/source | Inspected
assets/css/admin.css | .css | 7754 | Application/source | Inventory only
assets/css/booking.css | .css | 8066 | Application/source | Inventory only
assets/css/responsive-fix.css | .css | 5499 | Application/source | Inventory only
assets/css/scroll-car.css | .css | 2862 | Application/source | Inventory only
assets/css/styles.css | .css | 11609 | Application/source | Inventory only
assets/css/swiper-bundle.min.css | .css | 18431 | Application/source | Inventory only
assets/img/car-1.png | .png | 423629 | Asset/document | Inventory only
assets/img/car-2.png | .png | 452458 | Asset/document | Inventory only
assets/img/car-3.png | .png | 420556 | Asset/document | Inventory only
assets/img/ertiga.png | .png | 1688131 | Asset/document | Inventory only
assets/img/etios.png | .png | 1641587 | Asset/document | Inventory only
assets/img/favicon.png | .png | 1067 | Asset/document | Inventory only
assets/img/innova.png | .png | 1874009 | Asset/document | Inventory only
assets/js/booking.js | .js | 6444 | Application/source | Inspected
assets/js/gsap.min.js | .js | 72214 | Application/source | Inspected
assets/js/main.js | .js | 2142 | Application/source | Inspected
assets/js/scroll-car.js | .js | 6229 | Application/source | Inspected
assets/js/swiper-bundle.min.js | .js | 150447 | Application/source | Inspected
assets/uploads/.htaccess | [no extension] | 97 | Asset/document | Inventory only
assets/uploads/vehicles/vehicle-0455e8ddb90560bfee27.png | .png | 1396688 | Asset/document | Inventory only
assets/uploads/vehicles/vehicle-2627a308af903750f2f3.png | .png | 2041537 | Asset/document | Inventory only
assets/uploads/vehicles/vehicle-36e0f128ba7e1a7deb5e.png | .png | 1641587 | Asset/document | Inventory only
assets/uploads/vehicles/vehicle-47285ae299848e807264.png | .png | 420556 | Asset/document | Inventory only
assets/uploads/vehicles/vehicle-4f5934fffb90045372ff.png | .png | 1641587 | Asset/document | Inventory only
assets/uploads/vehicles/vehicle-537c58bf26eab27e530c.png | .png | 99853 | Asset/document | Inventory only
assets/uploads/vehicles/vehicle-5a1b7ad9b05f8d018c7f.png | .png | 1843444 | Asset/document | Inventory only
assets/uploads/vehicles/vehicle-64519916eae055b7d052.png | .png | 1843444 | Asset/document | Inventory only
assets/uploads/vehicles/vehicle-656ee130ab68df5173e8.png | .png | 1874009 | Asset/document | Inventory only
assets/uploads/vehicles/vehicle-70d207a1f6a4570c8478.png | .png | 1921004 | Asset/document | Inventory only
assets/uploads/vehicles/vehicle-8f0f2083961b68458160.png | .png | 1946203 | Asset/document | Inventory only
assets/uploads/vehicles/vehicle-aefda47690f01602a9f9.png | .png | 1641587 | Asset/document | Inventory only
assets/uploads/vehicles/vehicle-c0914fbe51399691a48b.png | .png | 1641587 | Asset/document | Inventory only
assets/uploads/vehicles/vehicle-ce17a2a14959870d5a19.png | .png | 1641587 | Asset/document | Inventory only
assets/uploads/vehicles/vehicle-dc5b3237d81bcc2ffe08.jpg | .jpg | 45321 | Asset/document | Inventory only
assets/uploads/vehicles/vehicle-e8b8dc5302c7d000b3c8.png | .png | 99853 | Asset/document | Inventory only
assets/uploads/vehicles/vehicle-f17f5d58ecd781e09d5c.png | .png | 1946203 | Asset/document | Inventory only
assets/uploads/vehicles/vehicle-fe062b31580f13c7c1a2.png | .png | 452458 | Asset/document | Inventory only
booking.php | .php | 88 | Application/source | Inspected
config/api_keys.php | .php | 0 | Application/source | Inspected
config/config.php | .php | 259 | Application/source | Inspected
config/database.php | .php | 1111 | Application/source | Inspected
contact.php | .php | 0 | Application/source | Inspected
controllers/BookingController.php | .php | 2398 | Application/source | Inspected
controllers/CustomerController.php | .php | 0 | Application/source | Inspected
controllers/RecommendationController.php | .php | 0 | Application/source | Inspected
controllers/TourController.php | .php | 0 | Application/source | Inspected
controllers/VehicleController.php | .php | 0 | Application/source | Inspected
database/002_content_management.sql | .sql | 3695 | Application/source | Inspected
database/003_backend_completion.sql | .sql | 2969 | Application/source | Inspected
database/005_vehicle_pricing.sql | .sql | 5457 | Application/source | Inspected
database/006_vehicle_pricing.sql | .sql | 442 | Application/source | Inspected
database/schema.sql | .sql | 8125 | Application/source | Inspected
destinations.php | .php | 1840 | Application/source | Inspected
includes/auth.php | .php | 1153 | Application/source | Inspected
includes/footer.php | .php | 0 | Application/source | Inspected
includes/functions.php | .php | 1701 | Application/source | Inspected
includes/header.php | .php | 0 | Application/source | Inspected
index.php | .php | 77429 | Application/source | Inspected
models/Booking.php | .php | 4803 | Application/source | Inspected
models/Cms.php | .php | 1150 | Application/source | Inspected
models/Customer.php | .php | 1627 | Application/source | Inspected
models/Destination.php | .php | 1777 | Application/source | Inspected
models/Driver.php | .php | 1743 | Application/source | Inspected
models/Service.php | .php | 2042 | Application/source | Inspected
models/TourPackage.php | .php | 2095 | Application/source | Inspected
models/Vehicle.php | .php | 4842 | Application/source | Inspected
tours.php | .php | 1806 | Application/source | Inspected
vehicles.php | .php | 49521 | Application/source | Inspected

## Requirements
Requirement Baseline
Requirements inferred from supplied source, scripts, SQL schema, and application documentation; confirm with product owner before formal sign-off.
Requirement ID | Requirement / Feature | Description | Type | Priority | Source / Trace
REQ-F-001 | Public home page | index.php loads branded landing page, navigation, hero, services, benefits, testimonials, and booking CTA. | Functional | High | index.php; assets/js/main.js
REQ-F-002 | Navigation and anchors | Header/footer links navigate to home anchors, vehicles, tours, destinations, and booking section. | Functional | High | *.php
REQ-F-003 | Responsive navigation | Mobile menu opens/closes and closes after selecting a link. | Functional/UI | High | assets/js/main.js
REQ-F-004 | Fleet catalogue | vehicles.php renders vehicle catalogue/cards, pricing/content and booking links. | Functional | High | vehicles.php; models/Vehicle.php
REQ-F-005 | Tour packages | tours.php renders active tour packages from the database. | Functional | Medium | tours.php; models/TourPackage.php
REQ-F-006 | Destinations | destinations.php renders active destinations/content. | Functional | Medium | destinations.php; models/Destination.php
REQ-F-007 | Booking form | Booking form captures name/contact, trip type, locations, date, participants and notes as applicable. | Functional | Critical | index.php; assets/js/booking.js
REQ-F-008 | Booking validation | Required fields, valid email/phone, date not in past, and participants 1–100 are enforced. | Functional | Critical | assets/js/booking.js; api/booking/create.php
REQ-F-009 | Booking submission | Valid booking posts FormData to api/booking/create.php and shows booking number on success. | Integration | Critical | api/booking/create.php; models/Booking.php
REQ-F-010 | Booking failure handling | API/network/database errors show a useful error and allow retry without duplicate submission. | Reliability | High | assets/js/booking.js
REQ-F-011 | CSRF protection | Booking creation rejects missing/invalid CSRF tokens. | Security | Critical | api/booking/create.php; includes/auth.php
REQ-F-012 | Admin authentication | Admin pages require authenticated admin session and logout invalidates access. | Security | Critical | includes/auth.php; admin/*.php
REQ-F-013 | Booking status workflow | Admin can transition booking status only among NEW, CONFIRMED, IN_PROGRESS, COMPLETED, CANCELLED. | Functional | High | api/booking/update-status.php
REQ-F-014 | Admin CRUD | Admin can manage customers, destinations, packages, services, vehicles, drivers, CMS and settings according to permissions. | Functional | High | admin/*.php
REQ-F-015 | Data integrity | Database constraints, required fields, unique license/settings/content keys, and foreign keys preserve integrity. | Data | High | database/*.sql
REQ-NF-001 | Performance | Core pages meet agreed response and page experience budgets under representative load. | Performance | High | All public pages
REQ-NF-002 | Accessibility | Keyboard access, labels, dialog semantics, color/contrast and screen-reader names are acceptable. | Accessibility | High | All public pages
REQ-NF-003 | Cross-browser | Supported Chrome, Firefox, Edge and Safari render and behave consistently. | Compatibility | Medium | All public pages
REQ-NF-004 | Mobile responsiveness | Layouts work at 360, 390, 768 and 1024 CSS px without horizontal scrolling or clipped controls. | Responsive | High | All public pages
REQ-NF-005 | Stability | Repeated navigation, refresh, booking retry and session expiry do not corrupt state or crash. | Reliability | High | All flows

## Test Data
Reusable Test Data
Use synthetic data only. Replace TD-001 date with a future date at execution time.
Data ID | Scenario | Name | Email | Phone | Trip Type | Source | Destination | Preferred Date | Participants | Notes | Expected Use
TD-001 | Valid booking baseline | Asha Sharma | asha.sharma@example.com | +918007961759 | ROUND_TRIP | Bengaluru Airport | Mysuru Palace | 2026-09-17 | 1 | Window seat requested | Expected valid; use future date if execution date differs.
TD-002 | Minimum participants | Ravi Kumar | ravi.kumar@example.com | +919876543210 | ONE_WAY | Delhi | Agra | 2099-01-01 | 1 |  | Valid boundary.
TD-003 | Maximum participants | Neha Singh | neha.singh@example.com | +919876543211 | ROUND_TRIP | Mumbai | Pune | 2099-01-01 | 100 | Large group | Valid boundary.
TD-004 | Zero participants | Test User | test@example.com | +919876543212 | ROUND_TRIP | A | B | 2099-01-01 | 0 |  | Invalid; below min.
TD-005 | Above maximum participants | Test User | test@example.com | +919876543212 | ROUND_TRIP | A | B | 2099-01-01 | 101 |  | Invalid; above max.
TD-006 | Past date | Test User | test@example.com | +919876543212 | ROUND_TRIP | A | B | 2020-01-01 | 1 |  | Invalid; date in past.
TD-007 | Blank required fields |  |  |  | ROUND_TRIP | [5 empty] | Invalid; required validation.
TD-008 | Invalid email | Test User | test@@example | +919876543212 | ROUND_TRIP | A | B | 2099-01-01 | 1 |  | Invalid format.
TD-009 | Boundary email length | AAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAA User | aaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaa@example.com | +919876543212 | ROUND_TRIP | A | B | 2099-01-01 | 1 |  | Validate max lengths/server handling.
TD-010 | Script injection strings | <script>alert(1)</script> | x@example.com | +919876543212 | ROUND_TRIP | <img src=x onerror=alert(1)> | B | 2099-01-01 | 1 | <svg/onload=alert(1)> | Must be encoded/rejected; no execution.
TD-011 | SQLi strings | A' OR 1=1 -- | sqli@example.com | +919876543212 | ROUND_TRIP | A' OR 1=1 -- | B | 2099-01-01 | 1 |  | Must not alter query or crash.
TD-012 | Malformed API | Missing CSRF and random fields | [8 empty] | API should reject safely with JSON error and 4xx.
TD-013 | Invalid status | [8 empty] | INVALID | API should reject status with 422.
TD-014 | Mobile viewport | [7 empty] | 360x800 |  | No overflow/clipping.
TD-015 | Desktop viewport | [7 empty] | 1440x900 |  | Full layout and readable content.

## Test Cases
Master Test Case Repository
Functional, smoke, sanity, regression, retest, positive, negative, boundary, exploratory, ad-hoc, UI, integration, system, E2E, performance, stability, compatibility, accessibility and responsive coverage.
Test Case ID | Requirement ID | Area | Title | Priority | Test Type | Preconditions | Steps | Test Data | Expected Result | Execution Status | Evidence / Defect ID
TC-F-001 | REQ-F-001 | Home | Load home page | Critical | Functional | Web server, PHP and DB configured | Open /index.php; wait for load | TD-015 | HTTP 200; title and hero render; no fatal error; primary CTA visible | Not Executed – environment setup required
TC-F-002 | REQ-F-001 | Home | Hero CTA to booking | High | Functional | Home loaded | Click Plan Your Journey / booking CTA | TD-015 | Viewport scrolls to booking section and form is visible | Not Executed – environment setup required
TC-F-003 | REQ-F-002 | Navigation | Validate header links | High | Functional | Home loaded | Click each header link and each anchor; use browser Back | TD-015 | Correct destination/anchor; no unexpected 404; active state is understandable | Not Executed – environment setup required
TC-F-004 | REQ-F-002 | Navigation | Validate footer links | Medium | Functional | Any public page loaded | Click footer Home, Solutions, Benefits, Contact/Booking, Our Fleet | TD-015 | Each link lands at intended page/section | Not Executed – environment setup required
TC-F-005 | REQ-F-003 | Mobile UI | Open and close mobile menu | High | Functional | Viewport 360x800 | Tap menu icon; verify menu; tap close; reopen and tap nav link | TD-014 | Menu opens, closes, and link selection closes menu; no body overflow | Not Executed – environment setup required
TC-F-006 | REQ-F-004 | Fleet | Load vehicle catalogue | High | Functional | DB has vehicle records | Open /vehicles.php; scroll cards; click a booking link | TD-015 | Cards, images, prices/content and booking links render; CTA reaches booking | Not Executed – environment setup required
TC-F-007 | REQ-F-005 | Tours | Load tour packages | Medium | Functional | DB has active package records | Open /tours.php | TD-015 | Active packages render; inactive packages excluded; empty state is graceful | Not Executed – environment setup required
TC-F-008 | REQ-F-006 | Destinations | Load destinations | Medium | Functional | DB has active destination records | Open /destinations.php | TD-015 | Active destinations/content render; no warnings or broken images | Not Executed – environment setup required
TC-F-009 | REQ-F-007 | Booking | Verify form controls | Critical | Functional | Home loaded | Inspect labels, defaults, radio buttons, date, participant, submit | TD-001 | All required controls present; ROUND_TRIP default; participants default 1; date min set to today | Not Executed – environment setup required
TC-F-010 | REQ-F-008 | Booking | Submit valid booking | Critical | Functional | DB/API available; valid CSRF session | Populate valid baseline; click Request a Ride | TD-001 | One request sent; loading state disables submit; success modal shows booking number; form resets | Not Executed – environment setup required
TC-F-011 | REQ-F-008 | Booking | Required field validation | Critical | Functional | Home loaded | Leave required fields blank; submit | TD-007 | Inline errors identify fields; error alert shown; no API request | Not Executed – environment setup required
TC-F-012 | REQ-F-008 | Booking | Invalid email validation | High | Functional | Home loaded | Enter TD-008; submit | TD-008 | Email error shown; no API request | Not Executed – environment setup required
TC-F-013 | REQ-F-008 | Booking | Past date rejected | High | Functional | Home loaded | Enter TD-006; submit | TD-006 | Date error says travel date cannot be in past; no API request | Not Executed – environment setup required
TC-F-014 | REQ-F-008 | Booking | Participant minimum boundary | High | Functional | Home loaded | Enter participants 1 then 0; submit each | TD-002; TD-004 | 1 accepted; 0 rejected with 1–100 message | Not Executed – environment setup required
TC-F-015 | REQ-F-008 | Booking | Participant maximum boundary | High | Functional | Home loaded | Enter 100 then 101; submit each | TD-003; TD-005 | 100 accepted; 101 rejected with 1–100 message | Not Executed – environment setup required
TC-F-016 | REQ-F-010 | Booking | API failure retry | High | Functional | Simulate 500/network offline | Submit valid form; restore network; submit again | TD-001 | Friendly error; loading clears; retry submits once; no duplicate record | Not Executed – environment setup required
TC-F-017 | REQ-F-009 | Booking | Success modal close paths | Medium | Functional | Successful booking created | Close via X, backdrop, Escape and Done in separate runs | TD-001 | Modal closes each way; body scroll restored; booking number visible before close | Not Executed – environment setup required
TC-F-018 | REQ-F-011 | Security | Missing CSRF | Critical | Functional | API reachable | POST valid booking without csrf_token | TD-012 | 4xx JSON response; record not inserted; no stack trace | Not Executed – environment setup required
TC-F-019 | REQ-F-011 | Security | Invalid CSRF | Critical | Functional | API reachable | POST valid booking with altered token | TD-012 | 4xx JSON response; record not inserted | Not Executed – environment setup required
TC-F-020 | REQ-F-012 | Admin | Unauthenticated admin redirect | Critical | Functional | Logged out | Open /admin/dashboard.php, /admin/bookings.php and entity pages | TD-015 | Redirect/login response; no protected data disclosed | Not Executed – environment setup required
TC-F-021 | REQ-F-012 | Admin | Admin logout | Critical | Functional | Authenticated admin | Open admin; click logout; revisit protected URL | TD-015 | Session destroyed; protected URL no longer accessible | Not Executed – environment setup required
TC-F-022 | REQ-F-013 | Admin | Valid booking status transitions | High | Functional | Authenticated admin; booking exists | Set NEW→CONFIRMED→IN_PROGRESS→COMPLETED; inspect DB/UI | TD-001 | Each valid transition persists and displays correct status | Not Executed – environment setup required
TC-F-023 | REQ-F-013 | Admin | Invalid booking status | High | Functional | Authenticated admin | POST update-status with INVALID status | TD-013 | 422 JSON error; status unchanged | Not Executed – environment setup required
TC-F-024 | REQ-F-014 | Admin | CRUD entities | High | Functional | Authenticated admin; DB available | Create/update/deactivate/delete or archive customer, package, destination, service, vehicle, driver | TD-001 | Valid changes persist; validation prevents bad data; UI reflects changes | Not Executed – environment setup required
TC-F-025 | REQ-F-015 | Data | Foreign key integrity | High | Functional | DB initialized | Attempt booking with nonexistent vehicle/driver; delete referenced entity | TD-012 | Invalid references rejected or nulled according to schema; no orphaned records | Not Executed – environment setup required
TC-F-026 | REQ-F-015 | Data | Unique constraint integrity | High | Functional | DB initialized | Insert duplicate driver license, content_key, setting_key | TD-012 | Duplicate rejected with controlled error; existing record unchanged | Not Executed – environment setup required
TC-S-001 | REQ-NF-002 | Accessibility | Keyboard-only booking | High | Accessibility | Home loaded | Use Tab/Shift+Tab/Enter; submit invalid form; open modal | TD-014 | Logical focus order; visible focus; every control operable; errors associated | Not Executed – environment setup required
TC-S-002 | REQ-NF-002 | Accessibility | Screen-reader names | High | Accessibility | Home loaded | Inspect accessibility tree for nav toggle, inputs, dialog, close buttons | TD-014 | Labels/names present; modal role, aria-modal, aria-labelledby work | Not Executed – environment setup required
TC-S-003 | REQ-NF-002 | Accessibility | Reduced motion | Medium | Accessibility | OS prefers-reduced-motion enabled | Load home and scroll | TD-014 | Swiper autoplay disabled/speed 0; reveal elements visible; no essential content hidden | Not Executed – environment setup required
TC-S-004 | REQ-NF-004 | Responsive | Responsive matrix | Responsive | Functional | Run at 360x800,390x844,768x1024,1024x768,1440x900 | TD-014; TD-015 | No horizontal scroll; content readable; controls usable; menu appropriate | High | Not Executed – environment setup required
TC-S-005 | REQ-NF-003 | Compatibility | Browser matrix | Compatibility | Functional | Run full smoke on Chrome, Firefox, Edge, Safari/iOS | TD-015 | Visual and functional parity; no console-breaking errors | High | Not Executed – environment setup required
TC-S-006 | REQ-NF-001 | Performance | Page performance budget | Performance | Functional | Lighthouse/DevTools on home, vehicles, tours | TD-015 | Record LCP/CLS/INP, TTFB, transfer size; compare against agreed budget; no blocking failure | High | Not Executed – environment setup required
TC-S-007 | REQ-NF-001 | Performance | Booking API latency | High | Performance | API and DB available | Submit 10 sequential and 20 concurrent valid requests in test environment | TD-001 | Record p50/p95/p99/error rate; no timeouts or duplicate IDs; thresholds agreed before release | Not Executed – environment setup required
TC-S-008 | REQ-NF-005 | Stability | Repeated navigation/refresh | High | Stability | Server available | Open/refresh each public page 20 times; scroll; open/close menus/modals | TD-015 | No crash, memory growth, broken state, or increasing error rate | Not Executed – environment setup required
TC-S-009 | REQ-NF-005 | Stability | Booking idempotency/retry | Critical | Stability | API available | Double-click submit; retry after timeout; inspect records | TD-001 | Button disabled during submit; one booking per intentional submission; no duplicates | Not Executed – environment setup required
TC-E-001 | REQ-F-009 | E2E | Visitor-to-admin booking lifecycle | Critical | End-to-End | DB/API/admin available | Visitor submits booking; admin views; confirms; assigns vehicle/driver; completes | TD-001 | Booking number created, record visible, status transitions and assignment persist end to end | Not Executed – environment setup required
TC-E-002 | REQ-F-014 | E2E | Content-to-public visibility | High | End-to-End | Admin authenticated | Create/activate destination/package/service; open public page | TD-001 | Published active content appears; inactive content is not public | Not Executed – environment setup required
TC-R-001 | REQ-F-001 | Regression | Public smoke pack | Critical | Regression | Build deployed | Run TC-F-001 through TC-F-008 | TD-015 | All core pages load and links work; release gate passes only if all critical cases pass | Not Executed – environment setup required
TC-R-002 | REQ-F-007 | Regression | Booking regression pack | Critical | Regression | Build deployed | Run TC-F-009 through TC-F-017 | TD-001; TD-007; TD-008; TD-006; TD-004; TD-005 | Form validation, success, failure and modal behavior unchanged | Not Executed – environment setup required
TC-R-003 | REQ-F-012 | Regression | Admin/security regression pack | Critical | Regression | Build deployed | Run TC-F-018 through TC-F-026 | TD-012; TD-013 | Auth, CSRF, statuses, CRUD and constraints remain secure and correct | Not Executed – environment setup required
TC-R-004 | REQ-NF-002 | Sanity | Post-fix sanity | High | Sanity | A defect fix deployed | Run impacted test plus home load, booking validation, login redirect | TD-001; TD-007 | Fix works and no immediate blocker in adjacent critical flows | Not Executed – environment setup required
TC-R-005 | REQ-F-008 | Retest | Defect retest template | High | Retest | Defect marked fixed | Execute original failing steps with original data and one nearby boundary | Defect-specific | Original expected result passes; evidence attached; regression impact assessed | Not Executed – environment setup required
TC-X-001 | REQ-F-001 | Exploratory | Explore broken links/empty data | Medium | Exploratory | Test environment | Navigate public site with DB empty, slow network, blocked images, JS disabled | TD-015 | Discoverability: no fatal errors; useful empty states; graceful degradation; log findings | Not Executed – environment setup required
TC-X-002 | REQ-F-007 | Ad Hoc | Rapid input abuse exploration | High | Ad-Hoc | Test environment | Paste emoji, Unicode, long strings, whitespace, newline, duplicate submit, browser back | TD-009; TD-010; TD-011 | No XSS/SQLi/crash; safe validation and controlled messages | Not Executed – environment setup required

## Execution Log
Test Execution Log
Populate Status, Actual Result, Evidence and Defect ID during execution. Recommended values: Pass, Fail, Blocked, Not Executed.
Test Case ID | Requirement ID | Test Case | Priority | Test Type | Status | Executed By | Execution Date | Expected Result | Actual Result | Evidence Link/Path | Defect ID
TC-F-001 | REQ-F-001 | Load home page | Critical | Functional | Not Executed – environment setup required |  |  | HTTP 200; title and hero render; no fatal error; primary CTA visible
TC-F-002 | REQ-F-001 | Hero CTA to booking | High | Functional | Not Executed – environment setup required |  |  | Viewport scrolls to booking section and form is visible
TC-F-003 | REQ-F-002 | Validate header links | High | Functional | Not Executed – environment setup required |  |  | Correct destination/anchor; no unexpected 404; active state is understandable
TC-F-004 | REQ-F-002 | Validate footer links | Medium | Functional | Not Executed – environment setup required |  |  | Each link lands at intended page/section
TC-F-005 | REQ-F-003 | Open and close mobile menu | High | Functional | Not Executed – environment setup required |  |  | Menu opens, closes, and link selection closes menu; no body overflow
TC-F-006 | REQ-F-004 | Load vehicle catalogue | High | Functional | Not Executed – environment setup required |  |  | Cards, images, prices/content and booking links render; CTA reaches booking
TC-F-007 | REQ-F-005 | Load tour packages | Medium | Functional | Not Executed – environment setup required |  |  | Active packages render; inactive packages excluded; empty state is graceful
TC-F-008 | REQ-F-006 | Load destinations | Medium | Functional | Not Executed – environment setup required |  |  | Active destinations/content render; no warnings or broken images
TC-F-009 | REQ-F-007 | Verify form controls | Critical | Functional | Not Executed – environment setup required |  |  | All required controls present; ROUND_TRIP default; participants default 1; date min set to today
TC-F-010 | REQ-F-008 | Submit valid booking | Critical | Functional | Not Executed – environment setup required |  |  | One request sent; loading state disables submit; success modal shows booking number; form resets
TC-F-011 | REQ-F-008 | Required field validation | Critical | Functional | Not Executed – environment setup required |  |  | Inline errors identify fields; error alert shown; no API request
TC-F-012 | REQ-F-008 | Invalid email validation | High | Functional | Not Executed – environment setup required |  |  | Email error shown; no API request
TC-F-013 | REQ-F-008 | Past date rejected | High | Functional | Not Executed – environment setup required |  |  | Date error says travel date cannot be in past; no API request
TC-F-014 | REQ-F-008 | Participant minimum boundary | High | Functional | Not Executed – environment setup required |  |  | 1 accepted; 0 rejected with 1–100 message
TC-F-015 | REQ-F-008 | Participant maximum boundary | High | Functional | Not Executed – environment setup required |  |  | 100 accepted; 101 rejected with 1–100 message
TC-F-016 | REQ-F-010 | API failure retry | High | Functional | Not Executed – environment setup required |  |  | Friendly error; loading clears; retry submits once; no duplicate record
TC-F-017 | REQ-F-009 | Success modal close paths | Medium | Functional | Not Executed – environment setup required |  |  | Modal closes each way; body scroll restored; booking number visible before close
TC-F-018 | REQ-F-011 | Missing CSRF | Critical | Functional | Not Executed – environment setup required |  |  | 4xx JSON response; record not inserted; no stack trace
TC-F-019 | REQ-F-011 | Invalid CSRF | Critical | Functional | Not Executed – environment setup required |  |  | 4xx JSON response; record not inserted
TC-F-020 | REQ-F-012 | Unauthenticated admin redirect | Critical | Functional | Not Executed – environment setup required |  |  | Redirect/login response; no protected data disclosed
TC-F-021 | REQ-F-012 | Admin logout | Critical | Functional | Not Executed – environment setup required |  |  | Session destroyed; protected URL no longer accessible
TC-F-022 | REQ-F-013 | Valid booking status transitions | High | Functional | Not Executed – environment setup required |  |  | Each valid transition persists and displays correct status
TC-F-023 | REQ-F-013 | Invalid booking status | High | Functional | Not Executed – environment setup required |  |  | 422 JSON error; status unchanged
TC-F-024 | REQ-F-014 | CRUD entities | High | Functional | Not Executed – environment setup required |  |  | Valid changes persist; validation prevents bad data; UI reflects changes
TC-F-025 | REQ-F-015 | Foreign key integrity | High | Functional | Not Executed – environment setup required |  |  | Invalid references rejected or nulled according to schema; no orphaned records
TC-F-026 | REQ-F-015 | Unique constraint integrity | High | Functional | Not Executed – environment setup required |  |  | Duplicate rejected with controlled error; existing record unchanged
TC-S-001 | REQ-NF-002 | Keyboard-only booking | High | Accessibility | Not Executed – environment setup required |  |  | Logical focus order; visible focus; every control operable; errors associated
TC-S-002 | REQ-NF-002 | Screen-reader names | High | Accessibility | Not Executed – environment setup required |  |  | Labels/names present; modal role, aria-modal, aria-labelledby work
TC-S-003 | REQ-NF-002 | Reduced motion | Medium | Accessibility | Not Executed – environment setup required |  |  | Swiper autoplay disabled/speed 0; reveal elements visible; no essential content hidden
TC-S-004 | REQ-NF-004 | Responsive matrix | Responsive | Functional | Not Executed – environment setup required |  |  | High
TC-S-005 | REQ-NF-003 | Browser matrix | Compatibility | Functional | Not Executed – environment setup required |  |  | High
TC-S-006 | REQ-NF-001 | Page performance budget | Performance | Functional | Not Executed – environment setup required |  |  | High
TC-S-007 | REQ-NF-001 | Booking API latency | High | Performance | Not Executed – environment setup required |  |  | Record p50/p95/p99/error rate; no timeouts or duplicate IDs; thresholds agreed before release
TC-S-008 | REQ-NF-005 | Repeated navigation/refresh | High | Stability | Not Executed – environment setup required |  |  | No crash, memory growth, broken state, or increasing error rate
TC-S-009 | REQ-NF-005 | Booking idempotency/retry | Critical | Stability | Not Executed – environment setup required |  |  | Button disabled during submit; one booking per intentional submission; no duplicates
TC-E-001 | REQ-F-009 | Visitor-to-admin booking lifecycle | Critical | End-to-End | Not Executed – environment setup required |  |  | Booking number created, record visible, status transitions and assignment persist end to end
TC-E-002 | REQ-F-014 | Content-to-public visibility | High | End-to-End | Not Executed – environment setup required |  |  | Published active content appears; inactive content is not public
TC-R-001 | REQ-F-001 | Public smoke pack | Critical | Regression | Not Executed – environment setup required |  |  | All core pages load and links work; release gate passes only if all critical cases pass
TC-R-002 | REQ-F-007 | Booking regression pack | Critical | Regression | Not Executed – environment setup required |  |  | Form validation, success, failure and modal behavior unchanged
TC-R-003 | REQ-F-012 | Admin/security regression pack | Critical | Regression | Not Executed – environment setup required |  |  | Auth, CSRF, statuses, CRUD and constraints remain secure and correct
TC-R-004 | REQ-NF-002 | Post-fix sanity | High | Sanity | Not Executed – environment setup required |  |  | Fix works and no immediate blocker in adjacent critical flows
TC-R-005 | REQ-F-008 | Defect retest template | High | Retest | Not Executed – environment setup required |  |  | Original expected result passes; evidence attached; regression impact assessed
TC-X-001 | REQ-F-001 | Explore broken links/empty data | Medium | Exploratory | Not Executed – environment setup required |  |  | Discoverability: no fatal errors; useful empty states; graceful degradation; log findings
TC-X-002 | REQ-F-007 | Rapid input abuse exploration | High | Ad-Hoc | Not Executed – environment setup required |  |  | No XSS/SQLi/crash; safe validation and controlled messages

## RTM Matrix
Requirements Traceability Matrix
Every baseline requirement is mapped to one or more test cases; “Coverage” is design coverage, not execution pass.
Requirement ID | Requirement | Priority | Linked Test Cases | Case Count | Coverage | Action
REQ-F-001 | Public home page | High | TC-F-001; TC-F-002; TC-R-001; TC-X-001 | 4 | Covered | Execute linked cases; close gaps before release
REQ-F-002 | Navigation and anchors | High | TC-F-003; TC-F-004 | 2 | Covered | Execute linked cases; close gaps before release
REQ-F-003 | Responsive navigation | High | TC-F-005 | 1 | Covered | Execute linked cases; close gaps before release
REQ-F-004 | Fleet catalogue | High | TC-F-006 | 1 | Covered | Execute linked cases; close gaps before release
REQ-F-005 | Tour packages | Medium | TC-F-007 | 1 | Covered | Execute linked cases; close gaps before release
REQ-F-006 | Destinations | Medium | TC-F-008 | 1 | Covered | Execute linked cases; close gaps before release
REQ-F-007 | Booking form | Critical | TC-F-009; TC-R-002; TC-X-002 | 3 | Covered | Execute linked cases; close gaps before release
REQ-F-008 | Booking validation | Critical | TC-F-010; TC-F-011; TC-F-012; TC-F-013; TC-F-014; TC-F-015; TC-R-005 | 7 | Covered | Execute linked cases; close gaps before release
REQ-F-009 | Booking submission | Critical | TC-F-017; TC-E-001 | 2 | Covered | Execute linked cases; close gaps before release
REQ-F-010 | Booking failure handling | High | TC-F-016 | 1 | Covered | Execute linked cases; close gaps before release
REQ-F-011 | CSRF protection | Critical | TC-F-018; TC-F-019 | 2 | Covered | Execute linked cases; close gaps before release
REQ-F-012 | Admin authentication | Critical | TC-F-020; TC-F-021; TC-R-003 | 3 | Covered | Execute linked cases; close gaps before release
REQ-F-013 | Booking status workflow | High | TC-F-022; TC-F-023 | 2 | Covered | Execute linked cases; close gaps before release
REQ-F-014 | Admin CRUD | High | TC-F-024; TC-E-002 | 2 | Covered | Execute linked cases; close gaps before release
REQ-F-015 | Data integrity | High | TC-F-025; TC-F-026 | 2 | Covered | Execute linked cases; close gaps before release
REQ-NF-001 | Performance | High | TC-S-006; TC-S-007 | 2 | Covered | Execute linked cases; close gaps before release
REQ-NF-002 | Accessibility | High | TC-S-001; TC-S-002; TC-S-003; TC-R-004 | 4 | Covered | Execute linked cases; close gaps before release
REQ-NF-003 | Cross-browser | Medium | TC-S-005 | 1 | Covered | Execute linked cases; close gaps before release
REQ-NF-004 | Mobile responsiveness | High | TC-S-004 | 1 | Covered | Execute linked cases; close gaps before release
REQ-NF-005 | Stability | High | TC-S-008; TC-S-009 | 2 | Covered | Execute linked cases; close gaps before release

## Defect Log
Defect Register and Fix Guidance
Defects marked potential/unverified require environment execution before being confirmed. Fix guidance is included for developer handoff and retest planning.
Defect ID | Title | Description / Risk | Category | Severity | Lifecycle Status | Source / Location | Reproduction and Fix Guidance | Evidence / Release Note
BUG-001 | Potential security defect | Booking API requires CSRF, but verify that token is rendered and refreshed on the public page before execution. | Security | Critical | Open – verify in environment | api/booking/create.php; includes/auth.php | Reproduce: open page, inspect csrf_token, submit valid request. Expected: token exists and valid request succeeds. Fix: render server-generated token, SameSite/session controls, reject missing/invalid token; add TC-F-018/019. | Unverified static risk
BUG-002 | Potential configuration defect | config/database.php contains blank password and setup-dependent DB connection; environment readiness is a release blocker. | Environment/Data | High | Open – environment dependency | config/database.php; SETUP-V2.md | Reproduce in clean env. Expected: documented secure configuration and health check. Fix: environment variables/secrets, fail-fast health check, never expose stack traces. | Requires deployment
BUG-003 | Potential authorization defect | Admin endpoint authorization and CSRF should be verified for every mutating admin action, not just booking API. | Security | Critical | Open – security verification required | admin/*.php; includes/auth.php | Attempt unauthenticated and cross-session mutation. Expected: 401/403 and no change. Fix: central middleware + CSRF on all mutations; add negative security tests. | Requires authenticated test environment
BUG-004 | Potential data validation defect | Client-side limits can be bypassed; server-side validation must enforce date, participants, formats and lengths. | Functional/Security | High | Open – API validation required | api/booking/create.php; models/Booking.php | POST invalid values directly. Expected: controlled 4xx; no insert. Fix: shared server validation and parameterized queries; add boundary/API tests. | Requires API execution
BUG-005 | Potential accessibility defect | Booking success modal closes and restores body scroll, but focus return/trap should be verified for keyboard and assistive technology. | Accessibility | Medium | Open – accessibility audit required | index.php; assets/js/booking.js | Open success modal with keyboard. Expected: focus moves into dialog and returns to trigger. Fix: focus management and inert background; add TC-S-001/002. | Requires browser audit

## Defect Lifecycle
Defect Life Cycle
Use this workflow for all confirmed defects and potential risks discovered during execution.
Stage | Activity / Exit Criteria | Artifact
1. New | Tester records reproducible issue with evidence, severity, priority and environment. | Defect Log
2. Triaged | QA lead/product owner validates scope, severity, priority and duplicate status. | Defect Log + triage meeting
3. Assigned | Developer/owner accepts defect and assigns target build. | Issue tracker
4. In Progress | Developer diagnoses root cause, implements fix and adds/updates unit/integration tests. | Source control + CI
5. Fixed | Developer supplies build/commit and deployment notes; never treat code change alone as proof. | Defect Log
6. Retest | Tester repeats original steps with same data and boundary/negative neighbors. | Execution Log
7. Reopened | If expected result still fails or regression appears, reopen with evidence and new details. | Defect Log
8. Closed | QA confirms fix, regression pack passes, evidence attached, and release risk accepted. | Defect Log + release gate
9. Deferred/Rejected/Duplicate | Document rationale, owner approval and revisit date; do not silently remove. | Defect Log

## STLC SDLC Plan
STLC and SDLC Operating Model
Use the workbook as the QA control document from requirement analysis through closure and maintenance.
Lifecycle / Phase | Activities | Outputs | Current State
STLC – Requirement Analysis | Identify public/admin/API/data/non-functional requirements; clarify acceptance criteria; map to REQ IDs. | Requirements; RTM | Complete baseline from source; product confirmation required
STLC – Test Planning | Define scope, risk, environment, tools, roles, entry/exit criteria, schedule and deliverables. | Read Me; Test Plan | Execute after environment is ready
STLC – Test Case Development | Design positive, negative, boundary, UI, integration, E2E, security, performance and accessibility cases. | Test Cases; Test Data | Design complete for inferred requirements
STLC – Environment Setup | Install PHP/MySQL, import SQL, configure secrets, seed admin/data, expose HTTP origin. | Environment checklist | Pending deployment
STLC – Test Execution | Run smoke, functional, integration, system, regression, non-functional and E2E tests; capture evidence. | Execution Log | Pending environment
STLC – Defect Reporting | Log defects with steps, expected/actual, severity, evidence, root cause and fix recommendation. | Defect Log | Static risks logged; execution confirmation pending
STLC – Closure | Summarize pass rate, residual risk, defect aging, quality metrics and sign-off. | Release report | Pending execution
SDLC – Discovery/Requirements | Confirm business goals, personas, flows, constraints and acceptance criteria. | Approved requirements | Recommended next step
SDLC – Design | Review UX, architecture, API, schema, security and responsive design. | Design review | Recommended next step
SDLC – Development | Implement with code review, secure validation, unit tests and migrations. | Commits/CI | Developer owned
SDLC – Testing | Use this workbook across test levels and quality attributes. | Execution Log/RTM | QA owned
SDLC – Release/Maintenance | Deploy, monitor, rollback, triage production issues, run regression after change. | Release checklist | Ops/Product owned

## QA QC Glossary
QA, QC and Test Strategy Glossary
Definitions and how to apply them to this website.
Concept | Definition / Purpose | Application to ARNA
Quality Assurance (process) | Prevent defects through requirements review, coding standards, secure design, peer review, test planning, CI and release gates. | Review requirements/RTM; review migrations; add server-side validation; enforce auth/CSRF; automate lint and regression.
Quality Control (product) | Detect defects through executed tests, inspections, audits and evidence. | Run the cases; record actual results; attach screenshots/logs; report and retest defects.
Functional Testing | Validate what the system does against requirements. | Public pages, booking, API, admin CRUD, statuses, data integrity.
Non-functional Testing | Validate how well it behaves. | Performance, stability, security, accessibility, compatibility, responsive behavior.
Smoke Testing | Broad shallow build acceptance. | Home, routes, booking page/form, admin redirect, core static assets.
Sanity Testing | Narrow post-change confidence. | Impacted fix plus critical adjacent flows.
Regression Testing | Detect unintended impact after changes. | Public smoke, booking regression, admin/security regression, responsive/accessibility checks.

## Non-Functional Plan
Non-Functional Testing Plan
Record measured results in Execution Log or attach an evidence report; thresholds must be agreed before release.
Quality Attribute | Test Approach | Acceptance / Evidence
Performance | Home/vehicles/tours/destinations: Lighthouse mobile + desktop; API load test; collect URL, date, device, throttling, LCP, INP, CLS, TTFB, FCP, TBT, bytes, requests, p50/p95/p99 and errors. | No universal threshold supplied; agree release budget, then gate on it. Recommended starting point: LCP ≤2.5s, INP ≤200ms, CLS ≤0.1, p95 API ≤1s in test environment.
Accessibility | Run Lighthouse/axe plus keyboard and screen-reader checks; verify labels, focus, modal semantics, contrast, reduced motion and alt text. | Record violations by impact and selector; no Critical/Serious violations at release.
Mobile responsiveness | Run 360x800, 390x844, 768x1024; test menu, cards, form, modal, horizontal overflow, touch targets. | Pass if no clipping/overflow and all tasks remain usable.
Desktop responsiveness | Run 1024x768 and 1440x900; test nav, grids, hero, forms, footer and wide images. | Pass if content is readable, aligned and no console-breaking layout error.
Cross-browser | Chrome, Firefox, Edge latest on desktop; Safari latest/iOS if available. | Run smoke + booking validation + modal + responsive critical paths.
Stability | 20 refresh/navigation cycles, repeated modal/menu actions, network interruption, retry, session expiry and duplicate submit. | Track crashes, console errors, memory/response degradation, duplicate records.
Security | CSRF, authz, input encoding, SQLi/XSS, session/logout, direct URL/API access, sensitive error disclosure. | Use TD-010/011/012 and authenticated test accounts; do not test production.

## Lighthouse Log
Lighthouse and Accessibility Results
Lighthouse requires a running HTTP URL. This log is intentionally unpopulated rather than inventing scores.
Run ID | URL | Device/Mode | Browser | Date | Performance | Accessibility | Best Practices | SEO | LCP | INP | CLS | TTFB | Evidence Path | Status
LH-001 | /index.php | Mobile simulated | Chrome | Not run | [8 empty] | Attach Lighthouse JSON/HTML | Not Executed
LH-002 | /index.php | Desktop | Chrome | Not run | [8 empty] | Attach Lighthouse JSON/HTML | Not Executed
LH-003 | /vehicles.php | Mobile simulated | Chrome | Not run | [8 empty] | Attach Lighthouse JSON/HTML | Not Executed
LH-004 | /tours.php | Mobile simulated | Chrome | Not run | [8 empty] | Attach Lighthouse JSON/HTML | Not Executed
LH-005 | /destinations.php | Mobile simulated | Chrome | Not run | [8 empty] | Attach Lighthouse JSON/HTML | Not Executed

## Executive Summary
Executive QA Summary
A truthful baseline: design and static inspection are complete; runtime testing requires deployment of the PHP/MySQL application.
Metric | Value | Interpretation
Files extracted | 166 | Inventory count from extracted tree
Requirements | 20 | Inferred baseline; confirm with product owner
Test cases | 44 | Designed coverage across requested testing types
Test data records | 15 | Reusable positive/negative/boundary/security/responsive data
Defects / risks logged | 5 | Potential findings awaiting execution confirmation
Execution status | Not executed – environment required | Browser/API/DB evidence is not available from ZIP alone
PHP lint | See /home/ubuntu/work/arna/php_lint.txt | Static syntax check artifact
Lighthouse | Not executed | Requires running HTTP origin and browser audit