## Executive Summary
Arna Tours & Travels — Complete Manual Testing Report
Field | Value | Metric | Value
Application URL | https://graceful-marigold-86dd01.netlify.app/#home | Performance | 59
Test date | 2026-09-17 | Accessibility | 93
Test type | Black-box manual testing + live DOM/asset inspection + Lighthouse | Best Practices | 100
Release scope observed | Single-page marketing/lead-generation site | SEO | 100
Overall status | CONDITIONAL PASS — static presentation works; performance/accessibility defects require remediation
Backend status | Not testable from public URL: no form, authentication, booking transaction, or exposed business API found
Confirmed critical/high defects | 0 critical; 2 high (performance/LCP and oversized image delivery)
Confirmed medium defects | 4 medium (contrast, touch targets, image sizing, render-blocking/unused assets)
Test cases executed | 27
Passed | 19
Failed | 6
Blocked / not applicable | 2
Lighthouse scores | Performance 59 ¦ Accessibility 93 ¦ Best Practices 100 ¦ SEO 100
Key evidence | HTTP 200; all discovered assets return 200; all in-page anchors resolve; images load; no forms; CTAs use tel:+918007961759
Limitations | No source repository, API contract, CMS/admin credentials, analytics access, real phone device, or backend environment was provided. Mobile score is not represented as a separate run because the local Playwright dependency was unavailable; mobile-responsive items are marked as observed/needs device confirmation where applicable.
Source-level conclusion | The uploaded archive contains a PHP/MySQL booking and admin system. Source review found 24 source QA findings, including high-risk configuration/upload/migration issues and an empty booking list API. Full runtime execution remains blocked until PHP + MySQL test environment and credentials are available.
Confirmed executable coverage | PHP syntax: 92/92 pass. Isolated PHP+MySQL integration: public pages, booking validation/creation, repeat customer behavior, admin setup/login, admin page access, status update, CSRF rejection, and migration failure were exercised. Original configuration still returns HTTP 500 on DB-backed public pages because database.php hardcodes root/empty password and no matching DB exists.

## Test Cases
TC ID | Area | Test scenario | Preconditions / test data | Steps | Expected result | Actual result / evidence | Status | Priority | Notes
TC-001 | Smoke | Open home URL | Public URL available | Navigate to URL | Page loads over HTTPS with brand, hero and navigation | HTTP 200; title “Arna Tours & Travels ¦ Premium Taxi & Chauffeur Services”; content rendered |  | P0
TC-002 | Smoke | Verify document language/title/meta | Public URL | Inspect page metadata | lang=en; meaningful title and description exist | lang=en; title present; description present |  | P1
TC-003 | Navigation | Home anchor | Page loaded | Click logo and Home | URL moves to #home and hero is visible | Resolved to #home |  | P1
TC-004 | Navigation | Services anchor | Page loaded | Click Services | URL moves to #services; services section visible | Resolved to #services and section visible |  | P0
TC-005 | Navigation | Fleet anchor | Page loaded | Click Our Fleet/Fleet | URL moves to #fleet; fleet section visible | Anchor target exists; static inspection confirms |  | P1
TC-006 | Navigation | About anchor | Page loaded | Click About | URL moves to #about; about section visible | Anchor target exists; static inspection confirms |  | P1
TC-007 | Navigation | Contact anchor | Page loaded | Click Contact | URL moves to #contact; contact CTA/footer visible | Anchor target exists; static inspection confirms |  | P1
TC-008 | CTA | Hero Book Your Ride | Phone-capable device or browser | Activate CTA | Phone dialer opens with intended number | href=tel:+918007961759; dialer action not executable in sandbox |  | P0 | Requires real-device confirmation
TC-009 | CTA | Header Book a Ride | Phone-capable device | Activate CTA | Phone dialer opens with intended number | href=tel:+918007961759 |  | P0 | Requires real-device confirmation
TC-010 | CTA | Service CTAs | Phone-capable device | Activate all four service CTAs | Each uses correct phone number and does not dead-link | All four use tel:+918007961759 |  | P1
TC-011 | Carousel | Next slide | Page loaded | Click Next slide repeatedly | Slide changes, image and indicator remain usable | Observed image changes across carousel; controls present |  | P1
TC-012 | Carousel | Previous slide | Carousel not at first slide | Click Previous slide | Previous slide appears without error | Control present; no runtime error observed |  | P2
TC-013 | Carousel | Slide indicators | Page loaded | Activate each of 3 indicators | Selected slide becomes visible and indicator state changes | Three indicators exposed with Go to slide labels |  | P2
TC-014 | Navigation | Mobile menu controls | Viewport under responsive breakpoint | Open/close menu | Menu opens and closes; links remain operable | DOM contains nav-toggle/nav-menu/nav-close; visual mobile state not device-verified |  | P1 | Needs physical/device or browser emulation confirmation
TC-015 | Content | Hero content | Page loaded | Review hero text and CTA | Headline, supporting text and CTA are readable and accurate | Content present and readable |  | P1
TC-016 | Content | Services completeness | Page loaded | Review four cards | Airport, Outstation, Corporate, Local Rentals each present | All four present |  | P1
TC-017 | Content | Fleet completeness | Page loaded | Review fleet section | Premium Sedan and Executive Ride with imagery present | Both present |  | P1
TC-018 | Content | Footer copyright/year | Page loaded | Scroll to footer | Footer shows brand, links, copyright year | Footer present; © 2026 shown |  | P2
TC-019 | Assets | Image loading | Page loaded | Inspect all images and natural dimensions | All images load and have meaningful alt text | 5 images loaded; all alt attributes present; each 1536x1024 natural size |  | P1
TC-020 | Assets | Static asset availability | Public URL | Request images/CSS/JS/favicon | All referenced assets return 200 | All discovered assets return 200 |  | P1
TC-021 | Regression | Reload from each section hash | Public URL | Load #home, #services, #fleet, #about, #contact | Correct section remains accessible after direct load | Anchors resolve from static inspection; no missing IDs |  | P1
TC-022 | Regression | Refresh after carousel interaction | Page loaded | Change slide then refresh | Page reloads cleanly and carousel initializes | Reload/navigation clean in browser; no console errors reported |  | P1
TC-023 | Accessibility | Keyboard/focus affordance | Browser keyboard | Tab through nav, CTAs, controls | All interactive elements reachable with visible focus | Not fully keyboard-verified in sandbox; Lighthouse flags contrast and touch targets |  | P1 | Run with keyboard-only checklist
TC-024 | Accessibility | Color contrast | Page loaded | Run Lighthouse/accessibility inspection | Text and controls meet WCAG contrast thresholds | Lighthouse accessibility 93; color-contrast audit failed |  | P1 | See BUG-003
TC-025 | Accessibility | Touch target size/spacing | Mobile viewport | Inspect CTA/menu/carousel controls | Targets at least 44x44 CSS px with spacing | Lighthouse target-size audit failed |  | P1 | See BUG-004
TC-026 | Performance | Initial load and LCP | Cold load | Run Lighthouse desktop default | LCP and initial load meet project budget | Performance 59; LCP 14.2s; TTI 14.2s; FCP 3.3s |  | P0 | See BUG-001/002
TC-027 | Performance | Network payload and image optimization | Cold load | Inspect Lighthouse payload and resources | Images are appropriately sized and modern format | 5,437 KiB total; next-gen image audit failed; responsive image audit failed |  | P0 | See BUG-002
TC-028 | Backend | Booking submission/API | API contract or test env required | Submit booking and verify persistence/notifications | Server validates, persists, and returns success/error | No form or exposed business API exists on public page |  | P0 | Needs backend URL/specification
TC-029 | Backend | Auth/session/security | Credentials and environment required | Login/logout/session expiry/authorization | Correct auth and access control | No auth surface or backend endpoint exposed |  | P0 | Needs backend scope

## Bugs
Bug ID | Severity | Priority | Title | Steps to reproduce | Expected | Actual / evidence | Root cause hypothesis | Recommended fix | Acceptance criteria | Status
BUG-001 | High | P0 | Very slow LCP/interactive readiness | Run Lighthouse against public URL with default desktop settings | LCP <2.5s; interactive page ready quickly | LCP 14.2s; TTI 14.2s; Performance 59; FCP 3.3s | Large hero image, render-blocking CSS/JS, delayed image discovery, server latency | Optimize critical rendering path; preload only the actual LCP image; defer noncritical JS; inline critical CSS; reduce animation work; verify CDN/server TTFB | LCP <=2.5s on agreed device/network; TTI <=5s; Lighthouse Performance >=90
BUG-002 | High | P0 | Hero/fleet PNG images are oversized and not responsive | Run Lighthouse and inspect network resources | Use WebP/AVIF and responsive srcset/sizes | Each car asset is 1536x1024 PNG; total payload 5,437 KiB; estimated image savings ~4.7 MiB; responsive image audit fails | Uncompressed/oversized PNGs served for all viewports | Convert to AVIF/WebP; create width variants; add width/height, srcset and sizes; lazy-load below-fold images; retain eager only for true LCP | No enormous-payload or modern-format audit failure; no layout shift; mobile image transfer materially reduced
BUG-003 | Medium | P1 | Insufficient color contrast | Run Lighthouse accessibility audit | All normal text and UI states meet WCAG AA contrast | Lighthouse color-contrast audit failed; accessibility 93 | Muted gray text and/or orange-on-light combinations are below threshold | Adjust text colors/backgrounds; validate normal text 4.5:1 and large text 3:1; test hover/focus/disabled states | Lighthouse color-contrast passes; manual contrast check passes
BUG-004 | Medium | P1 | Interactive touch targets too small or too tightly spaced | Run Lighthouse mobile accessibility audit | Touch targets >=44x44 CSS px and spaced adequately | Lighthouse target-size audit failed | Carousel indicators/arrows or compact links likely below target size | Increase button/link hit area with padding/min-width/min-height; separate adjacent targets; preserve visual design | Target-size audit passes on mobile viewport; no overlap or accidental activation
BUG-005 | Medium | P1 | Images have no explicit width/height attributes | Inspect DOM/Lighthouse | All content images reserve layout space | Lighthouse unsized-images audit partially fails; image elements lack explicit dimensions in DOM inspection | HTML relies on CSS only for intrinsic sizing | Add width and height attributes matching aspect ratio; keep CSS max-width:100% | Unsized-images audit passes and CLS remains <=0.1
BUG-006 | Medium | P1 | Render-blocking and unused resources increase startup cost | Run Lighthouse performance audit | Critical resources are minimized and noncritical resources deferred | Render-blocking resources, unused CSS and unused JS audits fail; external Remix Icon stylesheet is loaded | Global CSS/icon font and animation libraries load before first render | Inline critical CSS; defer noncritical CSS; remove unused rules/icons; defer GSAP/Swiper when not needed | Render-blocking and unused-resource audits pass or have documented budget exception
BUG-007 | Low | P2 | “Book a Ride”, “Enquire”, and “Get a quote” only dial a phone number | Activate CTAs on desktop/non-phone device | User gets a booking/enquiry path appropriate to the device | All booking-related CTAs are tel:+918007961759; no form, email, WhatsApp, or fallback displayed | Marketing copy implies booking/quote capability but implementation is phone-only | Provide responsive fallback: booking form or mailto/WhatsApp option with validation and privacy notice; retain tel on phones | Desktop users can submit or clearly access a non-phone contact method; leads are traceable

## Test Data
Data ID | Data / value | Used for | Expected handling | Observed result
TD-001 | https://graceful-marigold-86dd01.netlify.app/#home | Smoke/navigation | HTTPS page loads | HTTP 200
TD-002 | tel:+918007961759 | All booking/contact CTAs | Valid callable link; consistent number | Consistent across 8 CTA links
TD-003 | #home, #services, #fleet, #about, #contact | Anchor navigation | Each target exists | All targets exist
TD-004 | innova.png, ertiga.png, etios.png | Image/asset checks | HTTP 200, alt text, nonzero natural dimensions | All 200; all alt present; 1536x1024 natural dimensions
TD-005 | Desktop Lighthouse default | Performance | Record category scores and failed audits | Performance 59; A11y 93; BP 100; SEO 100
TD-006 | No form fields / no credentials | Backend scope | Mark backend tests N/A, do not fabricate results | 0 HTML forms; no business API surface
TD-007 | Mobile viewport requirement | Responsive checks | No horizontal overflow; menu/targets usable | Needs dedicated device/emulation confirmation; mobile-specific Lighthouse run unavailable in this session

## Lighthouse
Category / audit | Score | Display value | Severity | Finding | Recommended action
Performance | 59 |  | High | Overall performance score is 59 | Prioritize image delivery, LCP, render blocking, TTFB
Accessibility | 93 |  | Medium | Contrast and touch-target audits fail | Fix color tokens and target sizing
Best Practices | 100 |  | Pass | No category-level failure | Maintain
SEO | 100 |  | Pass | No category-level failure | Maintain
LCP | 0 | 14.2 s | High | Largest Contentful Paint is very slow | Optimize/preload hero image and critical CSS
FCP | 0.4 | 3.3 s | Medium | First contentful paint is slow | Reduce blocking work and payload
TTI | 0.09 | 14.2 s | High | Time to interactive is very slow | Defer scripts and reduce main-thread work
Total payload |  | 5,437 KiB | High | Page payload is large | Compress and resize images
Server response |  | 1,140 ms | High | Document response is slow | Improve hosting/cache/origin response
Modern image formats |  | Est. 4,734 KiB savings | High | PNG assets should be next-gen format | Serve AVIF/WebP
Responsive images |  | Est. 4,184 KiB savings | High | Images are not sized per viewport | Use srcset/sizes
Contrast |  | Failed | Medium | Insufficient contrast | Update foreground/background colors
Touch targets |  | Failed | Medium | Targets too small/close | Use 44x44 minimum hit areas
Unsized images |  | Partial fail | Medium | No explicit width/height | Add intrinsic dimensions
Render blocking |  | Est. 430 ms savings | Medium | CSS/resources block render | Inline/defer critical resources

## Responsive & Device
Viewport / device | Check | Expected | Observed evidence | Status | Follow-up
Desktop 1280x1100 | Initial render and section layout | No clipping/overflow; readable hero and cards | Browser screenshot rendered hero; sections and footer present |  | Retest on supported desktop browsers
Desktop | Horizontal overflow | scrollWidth equals viewport width | Browser DOM inspection showed scrollWidth 1265 at viewport 1280
Desktop | Carousel controls | Visible and operable | Previous/Next and 3 indicators exposed; slide changed
Mobile (not directly emulated) | Nav/menu | Menu opens/closes; links remain accessible | DOM includes nav-toggle/nav-menu/nav-close; not visually verified at phone width |  | Run Chrome device emulation or real iOS/Android
Mobile (not directly emulated) | Touch target sizing | >=44x44 CSS px | Lighthouse target-size audit failed |  | BUG-004
Mobile (not directly emulated) | Image transfer | Responsive source and modern format | Lighthouse responsive/modern image audits failed |  | BUG-002
Mobile (not directly emulated) | Text/contrast | Readable without zoom | Lighthouse contrast audit failed |  | BUG-003
Tablet | Layout breakpoint | Cards and hero adapt without overlap | Responsive stylesheet exists; no dedicated tablet run in this session |  | Run 768px emulation and capture evidence

## Backend Scope
Area | Test cases intended | Observed from public surface | Status | Required input to execute
Booking/API | Create booking, validation, duplicate handling, persistence, notification | No form; no booking endpoint visible; all CTAs are tel links |  | API base URL/OpenAPI, test credentials, database/notification expectations
Authentication | Login/logout/session expiry/password reset/authorization | No login or protected route |  | Auth environment and roles
Data validation | Required fields, formats, boundary values, injection/security | No data-entry fields |  | Form/API contract
Error handling | 4xx/5xx, timeout, retry, offline | No business requests observed |  | API contract and controlled failure environment
Security | Headers, CSP, cookies, secrets, rate limits | Only public static deployment inspected |  | Security test authorization and server headers/scope
Observability | Analytics, lead tracking, error logging | Not validated from public page |  | Analytics property/access and expected events

## Evidence & Limitations
Evidence ID | Evidence | Interpretation
EV-001 | Live URL returned HTTP 200 and page title matched brand | Deployment is reachable
EV-002 | All discovered in-page anchor IDs exist: home, services, fleet, about, contact | No broken anchor links found
EV-003 | All discovered image/script/CSS/favicon requests returned HTTP 200 | No broken static assets found
EV-004 | DOM contains 0 forms; no login; no business API request surface | Backend functional testing is blocked/not applicable from this URL
EV-005 | All eight booking/enquiry CTAs use tel:+918007961759 | Phone-only lead path; desktop fallback is absent
EV-006 | Lighthouse desktop: Performance 59, Accessibility 93, Best Practices 100, SEO 100 | Performance and accessibility require remediation
EV-007 | Lighthouse failed/flagged LCP 14.2s, total payload 5,437 KiB, modern image format, responsive images, contrast, touch targets, render-blocking, unsized images | Defects BUG-001 through BUG-006 are evidence-backed
EV-008 | Playwright package was unavailable in sandbox; separate mobile Lighthouse command rejected invalid preset | Mobile-specific visual/device claims are not overstated; rerun on Chrome emulation/real devices

## Source QA Findings
ID | Layer | Test / observation | Expected | Actual / source evidence | Status | Fix / acceptance criteria
SRC-001 | Packaging | Project root structure | One unambiguous deploy root | Archive contains ARNA-TOURS-TRAVELS and nested ARNA-TOURS-TRAVELS with differing index.php files; duplicate tree can cause wrong deploy target |  | Remove duplicate nested tree; deploy only the intended root; add CI packaging check
SRC-002 | Frontend | Public booking page route | booking.php renders booking form | booking.php only redirects to index.php#booking; form is embedded in index.php |  | Confirm all navigation/CTA links use #booking and preserve CSRF token
SRC-003 | Frontend | Client validation rules | Name, phone, locations, date, participants validated | booking.js validates name >=2, Indian mobile 6-9 + 9 digits, distinct locations, non-past date, participants 1-100 |  | Add server/client parity tests and localized error assertions
SRC-004 | Frontend | Booking AJAX submission | Successful response opens modal; failure preserves input and shows error | fetches api/booking/create.php; response JSON parsed; success resets form and opens modal |  | Add retry/timeout handling and prevent double submit on network edge cases
SRC-005 | Frontend | Date minimum timezone parity | Client and server agree on current date | JS uses browser local date; PHP uses Asia/Kolkata; users near midnight can see mismatch |  | Generate date min and validation from server timezone or explicit site timezone; test around midnight
SRC-006 | Frontend | Dynamic services/fleet content | Active DB records render with valid asset paths | Index loads Service::all(true); vehicles page loads available vehicles |  | Add empty/error state tests when DB unavailable or no records exist
SRC-007 | Frontend | Mobile responsiveness | Menu opens, links usable, no overflow | CSS includes 360/480/767/768-1024 breakpoints and 42px mobile menu button; runtime unavailable |  | Execute on Chrome mobile emulation and real iOS/Android; capture screenshots
SRC-008 | Backend | Booking CSRF and honeypot | Invalid token rejected; honeypot rejects bots | create.php validates CSRF before method check; website nonempty returns 422 |  | Return consistent content-type/status and log abuse safely
SRC-009 | Backend | Booking transaction | Customer and booking atomic | BookingController begins transaction, finds/updates/creates customer, creates booking, commits; rolls back Throwable |  | Integration test DB rollback and duplicate concurrent submissions
SRC-010 | Backend | Booking validation boundaries | Reject malformed, past, duplicate route and participants outside 1-100 | Server validation covers required values, mobile regex, same route, trip enum, exact date, past date, participant bounds |  | Add max length validation and Unicode/whitespace boundary cases
SRC-011 | Backend | Admin authentication | Inactive/invalid admin rejected; session rotates on login | Prepared query; status ACTIVE and password_verify required; session_regenerate_id(true) |  | Add rate limiting, generic timing-safe failure behavior, audit log
SRC-012 | Backend | Admin authorization | Unauthenticated admin/API access redirected/rejected | requireAdmin used in admin layout/API update-status/assign |  | Verify every admin endpoint and direct URL with session tests
SRC-013 | Backend | Status transitions | Only allowed statuses; update should report real update result | Allowed enum set enforced; model returns rowCount() >=0, which is true even when ID does not exist or value unchanged |  | Return false when no booking exists; enforce legal transition matrix if required; test 404/409 semantics
SRC-014 | Backend | Assignment integrity | Only existing/eligible vehicle and driver assigned | assign.php validates integer IDs but Booking::assign updates FK values without verifying record exists/availability; DB FK catches nonexistent IDs but business rules absent |  | Validate booking, vehicle, driver existence/status; prevent assigning inactive/maintenance/off-duty resources
SRC-015 | Backend | Booking list API | Endpoint returns authorized JSON list | api/booking/list.php is empty in archive |  | Implement or remove route; add auth, pagination, filters, JSON schema tests
SRC-016 | Backend | Controller/model completeness | Referenced classes available and functional | CustomerController, RecommendationController, TourController are empty files while related features/schema exist |  | Implement or remove unused routes; add coverage for each controller
SRC-017 | Security | Secrets/configuration | Credentials externalized and production-safe | database.php hardcodes root with empty password; config/api_keys.php empty |  | Use environment/secret manager, least-privilege DB user, fail closed in production
SRC-018 | Security | Security headers | Baseline headers configured | .htaccess only disables indexes/protects selected files; no CSP, HSTS, frame, referrer or MIME headers |  | Add headers appropriate to deployment and verify with security scanner
SRC-019 | Security | Upload validation | Only safe images stored outside executable path | MIME checked with finfo; random extension; uploads under assets/uploads/vehicles; no explicit re-encode, image dimensions, SVG, or server execution deny rule visible |  | Re-encode images, cap dimensions, deny script execution in upload directory, store outside web root where possible
SRC-020 | Security | Output encoding | DB/user content escaped in HTML | e() uses htmlspecialchars ENT_QUOTES UTF-8 across inspected pages |  | Retain; add XSS payload tests to every text field
SRC-021 | Database | Migration repeatability | Migrations rerunnable safely | 003_backend_completion.sql uses CREATE IF NOT EXISTS but unconditional ALTER TABLE ADD COLUMN/INDEX/CONSTRAINT; schema.sql already includes vehicle_id/driver_id and FKs |  | Make every ALTER conditional or split baseline/migration; test clean and already-migrated DBs
SRC-022 | Database | Pricing integrity | price_per_day equals rate_per_km * included_km | Admin vehicle save calculates round(rate*included,2) |  | Add DB constraint or service-level test to prevent direct inconsistent writes
SRC-023 | Database | Customer identity | One customer per mobile | findByMobile used but schema does not declare unique mobile_number |  | Add normalized unique index or define duplicate policy; test concurrent booking same mobile
SRC-024 | Operations | Error handling | Users see safe message; operators receive useful logs | DB failure dies with generic text; controllers log errors; no centralized correlation ID/monitoring visible |  | Use centralized structured logging and friendly error pages; test 500 behavior

## Backend Test Matrix
ID | Module | Scenario / test data | Expected | Source result / execution note | Status | Required runtime evidence
BE-001 | Booking API | GET /api/booking/create.php | 405 JSON invalid request | Code checks method after CSRF, so request without token returns 403 first |  | Run HTTP request and verify intended status/order
BE-002 | Booking API | POST missing CSRF | 403 JSON session expired | verifyCsrfToken rejects missing/invalid token |  | HTTP response/body assertion
BE-003 | Booking API | POST honeypot website=bot | 422 invalid submission | Silently rejects nonempty honeypot |  | HTTP response/body assertion
BE-004 | Booking API | Valid booking: Asha, 9876543210, Hubballi, Goa, ROUND_TRIP, future date, 2 | 200 success, booking number, DB customer+booking | Controller transaction and prepared inserts present; not executed without PHP/MySQL |  | Test DB and PHP runtime
BE-005 | Booking API | Invalid mobile: 12345 / 5123456789 | 422 precise mobile error | Regex rejects both |  | HTTP response/body assertion
BE-006 | Booking API | Past date / invalid date / same source-destination | 422 validation error | Explicit checks present |  | Boundary matrix with timezone
BE-007 | Booking API | participants 0, 101, nonnumeric | 422 participants error | ctype_digit and 1..100 checks present |  | HTTP response/body assertion
BE-008 | Booking API | DB failure during customer/booking insert | 500 safe JSON; transaction rollback | Throwable caught and rollback attempted |  | Kill DB or inject constraint failure
BE-009 | Admin login | Valid active hash credentials | Session regenerated; dashboard redirect; last_login updated | Code path present |  | Browser/session test with seeded admin
BE-010 | Admin login | Invalid/inactive credentials | Generic invalid error; no login | Code path present |  | Brute-force/rate-limit observation
BE-011 | Admin pages | Unauthenticated direct /admin/bookings.php | Redirect to admin login | admin-layout requires admin |  | HTTP/browser redirect test
BE-012 | Admin status | Existing booking status CONFIRMED | Status persists and view refreshes | Allowed values and prepared UPDATE present |  | DB assertion
BE-013 | Admin status | Nonexistent booking ID | 404/not found or false response | updateStatus may return true because rowCount() >= 0 |  | Fix result semantics and test nonexistent ID
BE-014 | Admin assign | Inactive vehicle/off-duty driver IDs | Reject assignment | No business eligibility validation present |  | Add model/service validation and test DB state
BE-015 | Admin CRUD | Service/vehicle add/edit/delete with bad CSRF | No mutation; friendly error | CSRF checks present |  | Browser and DB assertions
BE-016 | API inventory | GET /api/booking/list.php | Defined response or 404 | File is empty |  | Implement/remove endpoint and test contract

## Security & Code Review
ID | Control | Test / evidence | Finding | Severity | Recommendation
SEC-001 | Credentials | config/database.php lines 13-16 | Hardcoded root/empty DB password is unsafe and environment-specific | High | Use environment variables/secret manager and least privilege
SEC-002 | CSRF | functions.php + admin forms + booking API | CSRF token generated/session-bound and checked on mutating flows | Pass (source) | Add automated negative/positive CSRF tests
SEC-003 | SQL injection | Prepared statements in inspected models/controllers | Parameterized queries used for user-controlled values | Pass (source) | Continue code review for every future query
SEC-004 | XSS | e() used in public/admin output | HTML escaping is consistently present in inspected files | Pass (source) | Add payload regression suite
SEC-005 | Upload RCE | vehicles.php upload flow and upload directory | MIME validation exists but no deny-execution rule/re-encode/dimension cap visible | High | Harden upload storage and image processing
SEC-006 | HTTP headers | .htaccess | No CSP/HSTS/frame/referrer/MIME headers visible | Medium | Add and verify headers at web server/CDN
SEC-007 | Authentication abuse | admin/index.php | No rate limiting, lockout, MFA or audit log visible | Medium | Add rate limiting and admin audit trail
SEC-008 | Session security | auth.php | HttpOnly, SameSite=Lax and secure flag conditional on HTTPS; no explicit session.use_strict_mode or timeout | Medium | Enable strict mode, idle/absolute timeouts, secure production cookie policy
SEC-009 | Information exposure | DB failure path | Generic die message, but no unified error page; source/config files selectively denied | Medium | Deny all config/source extensions and use safe error handling
SEC-010 | Authorization scope | admin endpoints | requireAdmin applied in inspected routes | Pass (source) | Perform endpoint-by-endpoint direct access test

## Database & Migration
ID | Migration/schema area | Test | Finding | Status
DB-001 | schema.sql vs 003_backend_completion.sql | Apply baseline then completion migration | schema.sql already declares booking vehicle_id/driver_id and FKs; 003 unconditionally adds them again
DB-002 | 003_backend_completion.sql | Re-run completion migration twice | CREATE IF NOT EXISTS tables safe, ALTERs/constraints not idempotent
DB-003 | 002_content_management.sql | Re-run content migration | Tables IF NOT EXISTS and seed WHERE NOT EXISTS by title
DB-004 | 005_vehicle_pricing.sql | Run pricing migration on old/new schema | Column additions conditionally guarded by INFORMATION_SCHEMA; data updates/inserts are mostly repeat-safe
DB-005 | customers.mobile_number | Two concurrent bookings same mobile | Should converge to one customer if business rule requires uniqueness
DB-006 | bookings foreign keys | Delete customer/vehicle/driver with references | Customer delete restricts; vehicle/driver set null
DB-007 | booking status | Illegal sequence COMPLETED -> NEW | Should be rejected if lifecycle is enforced
DB-008 | pricing | rate 0 / included km extremes | Formula should be consistent and bounded

## Runtime Execution
Environment check | Expected | Observed | Status | Impact / next action
Archive extraction | Project extracts cleanly and one root is clear | Extracted, but duplicate nested project tree present with different index.php |  | Clean archive before deployment; verify intended root
PHP syntax lint | php -l passes every PHP file | Not executed initially because PHP CLI absent; installation attempted during assessment |  | Run php -l after runtime installation
PHP web server | Public pages return HTML | Could not start because PHP binary was absent at test time |  | Run PHP built-in server/Apache after install
MySQL connectivity | App connects to test DB | mysql client present; no configured test DB/credentials available |  | Provision isolated test DB and apply migrations
Browser functional testing | Booking form/admin UI/API workflows execute | Not executed against PHP app in sandbox |  | Run staging URL or local PHP+MySQL stack
Static source review | Routes, queries, validation and auth are inspectable | Completed across public/admin/API/model/schema files |  | Use findings in remediation sprint

## Project Inventory
Path / area | Count / size | QA relevance
PHP files | ~50+ across public/admin/api/controllers/models | Frontend, backend, auth, CRUD and API scope
Public pages | index.php, booking.php, destinations.php, tours.php, vehicles.php, contact.php | Functional navigation/content coverage
Admin pages | login, dashboard, bookings, customers, vehicles, services, packages, destinations, drivers, CMS, settings | CRUD, authorization, CSRF and workflow coverage
APIs | booking create/list/view/assign/update-status | Booking transaction and admin operations
Models | Booking, Customer, Vehicle, Driver, Service, CMS, Destination, TourPackage | Persistence/business-rule coverage
Migrations | schema.sql, 002, 003, 005, 006 | Fresh install, upgrade, idempotency and data integrity
Frontend assets | booking.js, styles, responsive CSS, images | Client validation, responsive behavior, performance

## Confirmed Execution
Test ID | Layer / route | Hands-on action and test data | Observed result | Status / evidence
RUN-001 | PHP source | php -l across all project PHP files | 92/92 files reported “No syntax errors detected”; 0 parse/fatal errors
RUN-002 | GET /index.php with original config | Start PHP server using project config without MySQL database | HTTP 500 “Database connection failed.”
RUN-003 | GET /admin/index.php with original config | Open admin login page without DB query | HTTP 200; login form and 64-character CSRF token rendered
RUN-004 | GET /api/booking/create.php | No CSRF token | HTTP 403 JSON: session expired
RUN-005 | Isolated GET /index.php | Run temporary copy against seeded MySQL test DB | HTTP 200; HTML response 79,144 bytes
RUN-006 | Isolated GET public pages | Open vehicles.php, destinations.php, tours.php | All returned HTTP 200; vehicles rendered seeded fleet
RUN-007 | Booking API invalid | Missing name; valid CSRF, future date, otherwise valid data | HTTP 422; “Please enter your full name.”
RUN-008 | Booking API invalid | Malformed date 2026-99-99 | HTTP 422; “Please select a valid travel date.”
RUN-009 | Booking API invalid | Same pickup/destination Goa/Goa | HTTP 422; route-difference message
RUN-010 | Booking API valid | Asha Test, 9876543210, Hubballi→Goa, ROUND_TRIP, 2026-10-01, 2 | HTTP 200; booking ARNA-20260917-48D1DA; booking_id 1
RUN-011 | Booking API repeat customer | Same mobile with renamed customer and second booking | HTTP 200; 1 customer row and 2 booking rows; customer name updated
RUN-012 | Admin setup/login | Create QA admin via setup, then login with valid password | Setup success; login HTTP 302 to dashboard; session cookie HttpOnly/SameSite=Lax
RUN-013 | Admin pages | Authenticated GET dashboard/bookings/customers/vehicles/services | All returned HTTP 200 with expected titles
RUN-014 | Admin status | Authenticated update booking 1 to CONFIRMED | Success message; DB status became CONFIRMED
RUN-015 | Admin assignment | Authenticated assignment of vehicle_id=9999, driver_id=9999 | No assignment persisted; generic failure path; FK protects data
RUN-016 | Admin API auth | POST update-status without session | HTTP 302 redirect to admin login
RUN-017 | Migration | Apply 003_backend_completion.sql after schema.sql | Exit 1: Duplicate column name vehicle_id
RUN-018 | Package integrity | Compare outer and nested project trees | Nested tree has a different index.php; archive has ambiguous deploy root